Engineering, Procurement & Construction Contract

Technical Annex No 1

SCOPE OF WORKS

| Complex: | OD-3 Sulphur Recovery Unit No.1 & Sulphur Recovery Unit No.2 |
| --- | --- |
| Project No. Title: | OLP02632 SRU K-1, K-2 and 10K-1 waste heat utilization for steam production using mechanical vapor recompression (MVR) technology |
| Part: | Process / Mechanical / Civil / Instrument / Electrical |
| Type of Contract: Revision: | EPC 0 |

Table of Contents

| 1 | GENERAL | 3 |
| --- | --- | --- |
| 1.1 | SUBJECT MATTER | 3 |
| 1.2 | INTRODUCTION | 3 |
| 1.3 | DEFINITIONS | 4 |
| 1.4 | GENERAL WORKS DESCRIPTION | 4 |
| 1.5 | BATTERY LIMITS | 6 |
| 1.6 | BASIC INFORMATION | 16 |
| 1.7 | LIST OF ATTACHMENTS | 16 |
| 2 | PARTICULAR REQUIREMENTS | 18 |
| 2.1 | QUALIFICATION REQUIREMENTS FOR CONTRACTOR | 18 |
| 2.2 | DOCUMENTATION | 19 |
| 2.3 | MANUFACTURING REQUIREMENTS | 20 |
| 2.4 | PAINTING | 20 |
| 2.5 | WELDING | 20 |
| 2.6 | NOZZLE CONNECTION | 20 |
| 2.7 | MATERIALS AND EQUIPMENT | 20 |
| 2.8 | NAMEPLATE | 21 |
| 2.9 | INSPECTION AND TESTING | 21 |
| 2.10 | TRAINING | 21 |
| 2.11 | ESTIMATION AND SCHEDULE | 21 |
| 3 | SCOPE OF WORKS | 22 |
| 3.1 | PROJECT MANAGEMENT AND SITE SUPERVISION | 22 |
| 3.2 | ENGINEERING | 22 |
| 3.3 | MATERIAL PROCUREMENT AND SUBCONTRACTING | 25 |
| 3.4 | ERECTION / INSTALLATION | 27 |
| 4 | TEMPORARY CONSTRUCTION FACILITIES AND UTILITIES | 29 |
| 5 | SCHEDULING AND REPORTING | 30 |
| 6 | DATA REQUIREMENTS | 31 |
| 7 | CLEANUP, SAFETY, WORK RULES AND REGULATIONS | 33 |
| 8 | QUALITY PROGRAM REQUIREMENTS | 34 |
| 9 | CONSTRUCTION | 35 |

## 1	GENERAL

- 1.1	SUBJECT MATTER

- OS-3 Sulphur Recovery Unit No.1 (hereinafter - SRU-1) has two MEA regeneration (desorption) blocks with columns K-1 and K-2, and Sulphur Recovery Unit No.2 (hereinafter - SRU-2) has one MEA regeneration (desorption) block with column 10K-1. MEA regeneration blocks are designed to perform the regeneration of saturated MEA (mono-ethanol-amine) solution of 10-20 %.

- Gas & vapor mixture (acid gas & water vapor) of about 107 °C  released from the saturated MEA solution at the top of columns K-1, K-2 and 10K-1 is cooled in the air coolers-condensers and water coolers, and then sent to the separators. The process described above generates a significant amount of waste heat that is emitted to atmosphere through the air coolers.

- The objective of the project is to introduce MVR technology in SRU-1 and SRU-2 to recover the waste heat from the overhead streams of columns K-1, K-2 and 10K-1 for the production of low pressure steam. The new MVR systems must have the flexibility that allows adjusting their load based on the market price of electricity.

- Each column would be equipped with an evaporator for the production of low (vacuum) pressure saturated steam. Then the steam from the evaporators would be sent to a steam compressors where it would be compressed to the required pressure of approximately 3 barg. The vacuum in evaporators would be created with the use of steam compressors. The steam produced in the evaporators and compressed by the compressors would be supplied to the reboilers for the preheating of the columns K-1, K-2 and 10K-1, ensuring the possibility to send the excess steam to Amin Regeneration Unit No.4 (hereinafter - ARU-4).

- 1.2	INTRODUCTION

This ANNEX defines the scope of work, supply and services CONTRACTor shall undertake to design, procure, construct, erect, commission and start-up of Mechanical Vapor Recompression systems (hereinafter MVR) for steam production at SRU-1 & SRU-2 in AB ORLEN Lietuva (hereinafter OL or OWNER) in Mažeikiai, Lithuania.

CONTRACTOR shall, in accordance with the requirements of this CONTRACT, the ANNEXES and the latest editions of all current Lithuanian and European regulations, design, engineer, procure and supply all necessary equipment and materials, perform all shop and field inspection and testing, erect, install, commission, test, start-up, run performance tests and otherwise perform all activities required for the installation of three MVR systems, including special type evaporators for steam production, steam compressors and other auxiliary equipment at SRU-1 & SRU-2 units, hereinafter called “WORKS”

This Scope of Work may not be complete in every detail but, when taken in conjunction with the Technical Annexes, Engineering Design Data, other OL standards and other regulations, is deemed to be sufficient to allow the CONTRACTOR to prepare his detailed design and to construct and complete the WORKS.

CONTRACTOR guaranties the fulfilment of guarantee figures laid down by in Contract Technical Annexes.  CONTRACTOR guaranties the designed new evaporators and steam compressors as well as all supplied equipment to be operated in accordance with the TECHNICAL DOCUMENTATION and OPERATING MANUAL to meet Key Product Quality of processes as specified in Technical Annexes of the CONTRACT.

- 1.3	DEFINITIONS

PLANT shall mean new evaporators TK-13, TK-14 & 10TK-3, steam compression systems and related existing equipment as Columns K-1, K-2, 10K-1, air coolers AO-1A, B, C, D, AO-2, AO-3, 10AO-2A, B, C, D and territory around said equipment at SRU-1 & SRU-2 units within BATTERY LIMITS and present Scope of Works to be designed, built and located at OWNER’S territory and to be owned and operated by the OWNER, as defined in the CONTRACT.

WORKS shall mean all works, services and supplies required to be performed by CONTRACTOR in order to design, engineer, procure and supply all necessary equipment and materials, perform all shop and field inspection and testing, erect, install, commission, test, start-up, run performance tests and otherwise perform all activities required for the installation of MVR systems, including special type evaporators for steam production, steam compressors and other auxiliary equipment at SRU-1 & SRU-2 units within BATTERY LIMITS and present scope of work.

CONTRACT EFFECTIVE DATE means the day CONTRACT is signed by both PARTIES.

- 1.4	GENERAL WORKS DESCRIPTION

CONTRACTOR shall, in accordance with the requirements of this CONTRACT, the ANNEXES and the latest editions of all current Lithuanian and European regulations, design, engineer, procure and supply all necessary equipment and materials, to perform all shop and field inspection and testing, erect, install, and commission and test, and otherwise perform all activities required for the installation of MVR systems, including special type evaporators for steam production, steam compressors and other auxiliary equipment at SRU-1 & SRU-2 units. The WORKS generally consists of new three MVR systems installation which includes the following main activities:

- CONTRACTOR shall obtain all planning, building, construction or other permits, licenses or approvals as required by applicable law in relation to the design, execution, construction, certification and operation of the PLANT, including the remedying of any defects therein. CONTRACTOR shall give all notices, pay all taxes, duties and fees that may be necessary to obtain such permits, licenses and approvals and CONTRACTOR shall indemnify and hold OWNER harmless against and from the consequences of any failure to do so. The TECHNICAL DOCUMENTATION and information necessary to obtain these permits shall be prepared and provided by CONTRACTOR in accordance with the CONTRACT, applicable laws and regulations. CONTRACTOR shall obtain all necessary permits and approvals in a timely manner in accordance with the TIME SCHEDULE and the TIME FOR COMPLETION;

- Preparation of project proposal and technical/detailed design, which should include an explanatory note, PFD and P&ID, heat and mass balance, cause and effect diagram, equipment and instrument data sheets, instrument list, start-up, operation and stop instruction, energy utilities diagram on B.L., Unit Emergency shutdown / trip instruction and other documentation necessary for project implementation;

- Implementation of HAZOP and SIL determination/verification;

- Modification of P&ID based on HAZOP and SIL recommendations;

- Implementation of Detail Design including process, mechanical, civil, instrument/control and electrical parts;

- Procurement, fabrication and delivery at site of three special (vacuum at steam side of evaporator) type evaporators and steam compressors (which should be installed in new containers in non Ex zone) as well as all other related equipment;

- Design and installation of new transformer substation(s), intended for power supply of electric motors of steam compressors and additional equipment, and connection of new electrical equipment;

- Design and installation of a new electric cables from the existing TP-110/6 kV "Juodeikiai" transformer substation to the new transformer substation(s);

- Implementation of the civil part of the project, including the installation of buildings/containers for steam compression systems, changing the configurations of necessary underground communications, installation of foundations for evaporators and buildings/containers, installation of supporting structures, installation of service areas, stairs and ladders according to the new detailed project OLP02632;

- Attachment#1 to STC ANNEX1 - Technological design proposal, the locations of the equipment shown in file 1.38 are preliminary. The Owner does not know the dimensions of the new equipment and the Contractor will have to revise the layout of the equipment when preparing the design.

- Installation of the new special type evaporators and steam compression systems according to the new Detail Design OLP02632;

- Installation of new process and utility pipelines according to the new Detail Design OLP02632 and modification of existing pipelines necessary for project implementation and in order to connect to Project ISBL  side;

- If the implementation of the project is obstructed by the existing pipelines or structures, they will have to be dismantled and re-installed after the completion of the project, expertise of the piperack/structures.

- Installation of new Evaporator’s TK-13, TK-14, 10TK-3 platforms, stairs and ladders according to the new Detail Design OLP02632;

- Installation of new Instrumentation and Electrical equipment according to the new Detail Design OLP02632. CONTRACTOR should foresee that some of the Instrumentation and Electrical equipment will be in Ex zone.

- Provide all other necessary works and services to reach the targets set above;

- All necessary documentation preparation activities.

The contract shall include all works that are described or specified in the drawings, specifications or other documents indicated in the present Scope of WORKS. Any minor works not specified in drawings or other documents but are required in order to ensure work functionality and completeness shall be considered as included into the Contract price. The Contractor shall analyse the provided documentation and all arisen issues shall solve with the Owner. The Contractor shall comply with all work-related requirements as provided by the Owner.

- 1.5	BATTERY LIMITS

- Battery limits of the Scope of WORKS are determined in attached technological design proposal “OLPP115” and described in present SOW. Some Battery Limits shown only preliminary and shall be clarified during Detail Design:

| # | Description | - Battery Limit | - Battery Limit | - Reference |
| --- | --- | --- | --- | --- |
| - Engineering |  |  |  |  |
| 1 | Detail Design | - Within CONTRACTOR’s scope of WORKS including: - - Explanatory note (process description) preparation; - - PFD and P&ID preparation; - - Heat and mass balance preparation; - - Cause and effect diagram preparation; - - Equipment and instrument datasheets preparation; - - Instrument list preparation; - - Start-up, operation, stop and Emergency shutdown / trip instruction preparation; - - HAZOP and SIL determination/ verification; - - Modification of P&ID and other documentation based on HAZOP recommendations; | - CONTRACTOR’s Scope of WORKS | - For details see attachments#1, 2, 3, 4. |
|  |  | - - Process, Mechanical, Civil, Instrument, Electrical and Fireproofing parts preparation as per contract requirements; - 3D model of new evaporators TK-13, TK-14, 10TK-3, steam compressors including existing equipment K-1, K-2, 10K-1 AO-1/A, B, C, D, AO-2, AO-3, 10AO-2A, B, C, D and pipelines preparation and submission; - Note: CONTRACTOR’S Detail Design will be deemed as prepared only when will be approved by OWNER and issued as “ISSUE FOR CONSTRUCTION” version |  |  |
| - Process part |  |  |  |  |
| 2 | New special type, vacuum evaporator TK-13 for column K-1 | - New special type evaporator TK-13 (process gas / BFW (L.P. saturated steam)) suitable for MVR technology applications are within CONTRACTORS’s Scope of Works fully equipped as per worldwide best practice including engineering, design, manufacturing, delivery, installation, water circulation pumps (if any), safety and relief valves, instrumentation & electrical equipment, lifting lugs, service platforms, access routes, manholes, piping, painting, thermal insulation and related equipment | - CONTRACTOR’s Scope of WORKS | - For details see attachments#1, 2, 3, 4. |
| 3 | New special type, vacuum evaporator TK-14 for column K-2 | - New special type evaporator TK-14 (process gas / BFW (L.P. saturated steam)) suitable for MVR technology applications are within CONTRACTORS’s Scope of Works fully equipped as per worldwide best practice including engineering, design, manufacturing, delivery, installation, water circulation pumps (if any), safety and relief valves, instrumentation & electrical equipment, lifting lugs, service platforms, access routes, manholes, piping, painting, thermal insulation and related equipment | - CONTRACTOR’s Scope of WORKS | - For details see attachments#1, 2, 3, 4. |
| 4 | New special type, vacuum evaporator 10TK-3 for column 10K-1 | - New special type evaporator 10TK-3 (process gas / BFW (L.P. saturated steam)) suitable for MVR technology applications are within CONTRACTORS’s Scope of Works fully equipped as per worldwide best practice including engineering, design, manufacturing, delivery, installation, water circulation pumps (if any), safety and relief valves, instrumentation & electrical equipment, lifting lugs, service platforms, access routes, manholes, piping, painting, thermal insulation and related equipment | - CONTRACTOR’s Scope of WORKS | - For details see attachments#1, 2, 3, 4. |
| 5 | New steam compression system for column K-1 | - Within CONTRACTOR’s Scope of WORKS fully equipped as per worldwide best practice including engineering, design, manufacturing, delivery, assembling and installation, steam compressors, compressors lubrication and cooling systems (if necessary), compressors sealing system, gaskets, steam desuperheating system, steam traps for removing condensate between compressors (if necessary), condensate tank and pump (if necessary), safety valves, instrumentation & electrical equipment, piping, painting, thermal insulation and related equipment. CONTRACTOR should provide Coefficient of Performance (hereinafter – COP) of the system at minimum, normal and maximum unit capacity. | - CONTRACTOR’s Scope of WORKS | - For details see attachments#1, 2, 3, 4. |
| 6 | New steam compression system for column K-2 | - Within CONTRACTOR’s Scope of WORKS fully equipped as per worldwide best practice including engineering, design, manufacturing, delivery, assembling and installation, steam compressors, compressors lubrication and cooling systems (if necessary), compressors sealing system, gaskets, steam desuperheating system, steam traps for removing condensate between compressors (if necessary), condensate tank and pump (if necessary), safety valves, instrumentation & electrical equipment, piping, painting, thermal insulation and related equipment. CONTRACTOR should provide Coefficient of Performance (hereinafter – COP) of the system at minimum, normal and maximum unit capacity. | - CONTRACTOR’s Scope of WORKS | - For details see attachments#1, 2, 3, 4. |
| 7 | New steam compression system for column 10K-1 | - Within CONTRACTOR’s Scope of WORKS fully equipped as per worldwide best practice including engineering, design, manufacturing, delivery, assembling and installation, steam compressors, compressors lubrication and cooling systems (if necessary), compressors sealing system, gaskets, steam desuperheating system, steam traps for removing condensate between compressors (if necessary), condensate tank and pump (if necessary), safety valves, instrumentation & electrical equipment, piping, painting, thermal insulation and related equipment. CONTRACTOR should provide Coefficient of Performance (hereinafter – COP) of the system at minimum, normal and maximum unit capacity. | - CONTRACTOR’s Scope of WORKS | - For details see attachments#1, 2, 3, 4. |
| 8 | HVAC for existing substation TP-16 JVS3 | - Within CONTRACTOR’s Scope of WORKS including engineering, design, manufacturing, delivery, installation, new Heating, Ventilation and Air Conditioning system (hereinafter - HVAC), suction of hot air from VFD’s, fire protection systems |  | - For details see attachments#1, 2, 3, 4. |
| 9 | HVAC for existing substation TP-74 | - Within CONTRACTOR’s Scope of WORKS including engineering, design, manufacturing, delivery, installation, new air conditioning system, suction of hot air from VFD’s, fire protection systems |  | - For details see attachments#1, 2, 3, 4. |
| 10 | HVAC for new module substation(s) | - Within CONTRACTOR’s Scope of WORKS including engineering, design, manufacturing, delivery, installation, new HVAC system, fire protection systems |  | - For details see attachments#1, 2, 3, 4. |
| 11 | HVAC for steam compression systems containers | - Within CONTRACTOR’s Scope of WORKS including engineering, design, manufacturing, delivery, installation, new HVAC system, fire protection systems |  | - For details see attachments#1, 2, 3, 4. |
| 12 | Pipelines | - Within CONTRACTOR’s Scope of WORKS including engineering, design, manufacturing, delivery, installation, reconfiguration of existing pipelines | - CONTRACTOR’s Scope of WORKS within indicated B.L. | - For details see attachments#1, 2, 3, 4. |
| 12.1 | v. A-3-1-1, process gas from column K-1 to TK-13 evaporator | - From BL1 on process gas pipeline 500-HS-A-3-1-1-N-N to evaporator TK-13 and to BL3 including instrument PT-2005 and pipeline’s v. A-3-1-1 thermal insulation from column K-1 to evaporator TK-13 | - 1, 3 | - For details see attachment#1 |
| 12.2 | v. A-3-1-1, process gas from evaporator TK-13 to air coolers AO-1A,B,C,D | - From BL4 on process gas pipeline 500-HS-A-3-1-1-N-N to evaporator TK-13 including instrument PT-2004 | - 4 | - For details see attachment#1 |
| 12.3 | v. A-3-1-2, process gas from column K-2 to TK-14 evaporator | - From BL10 on process gas pipeline 500-HS-A-3-1-2-N-N to evaporator TK-14 and to BL12 including instrument PT-2130 and pipeline’s v. A-3-1-2 thermal insulation from column K-2 to evaporator TK-14 | - 10, 12 | - For details see attachment#1 |
| 12.4 | v. A-3-1-2, process gas from evaporator TK-14 to air coolers AO-2, AO-3 | - From BL13 on process gas pipeline 500-HS-A-3-1-2-N-N to evaporator TK-14 including instrument PT-2101 | - 13 | - For details see attachment#1 |
| 12.5 | v. L-10-3-1, process gas from column 10K-1 to 10TK-3 evaporator | - From BL14 on process gas pipeline 500-HS-L-10-3-1-N-N to evaporator 10TK-3 and to BL16 including instrument PT-2242 and pipeline’s v. L-10-3-1 thermal insulation from column 10K-1 to evaporator 10TK-3 | - 14, 16 | - For details see attachment#1 |
| 12.6 | v. L-10-3-1, process gas from evaporator 10TK-3 to air coolers 10AO-2A,B,C,D | - From BL17 on process gas pipeline 500-HS-L-10-3-1-N-N to evaporator 10TK-3 including instrument PT-2441 | - 17 | - For details see attachment#1 |
| 12.7 | v. 5-3-5-4, boiler feedwater from pumps S-16 & S-17 to evaporator TK-13 | - From BL7 on boiler feed water pipeline 100-SCL-5-3-3-1-N-N to evaporator TK-13 and to steam desuperheater including instruments FT-3001, LV-4000 and other instruments according to the new Detail Design | - 7 | - For details see attachment#1 |
| 12.8 | v. 5-3-5-4, boiler feedwater from pumps S-16 & S-17 to evaporator TK-14 | - From BL8 on boiler feedwater pipeline 100-SCL-5-3-3-1-N-N to evaporator TK-14 and to steam desuperheater including instruments FT-3002, LV-4100 and other instruments according to the new Detail Design | - 8 | - For details see attachment#1 |
| 12.9 | v. L-208, boiler feedwater from pumps 20S-1 & 20S-2 to evaporator 10TK-3 | - From BL20 on boiler feedwater pipeline 50-SCM-L-200-HC-N to evaporator 10TK-3 and to steam desuperheater including instruments FT-3510, LV-4201 and other instruments according to the new Detail Design | - 20 | - For details see attachment#1 |
| 12.10 | v. G-4-2-1, steam from steam compressors to TK-7, TK-8 | - From BL6 on steam pipeline 250-SSL-G-4-2-1-HC-N to steam compressors including sample point for analyses, analyser QT-TK-13 and instruments FT-3005, PT-2002, TE-1001 | - 6 | - For details see attachment#1 |
| 12.11 | v. G-4-1-2, steam from steam compressors to TK-9, TK-10 | - From BL9 on steam pipeline 250-SSL-G-4-1-2-HC-N to steam compressors including sample point for analyses, analyser QT-TK-14 and instruments FT-3121, PT-2100, TE-1100 | - 9 | - For details see attachment#1 |
| 12.12 | v. L-192, steam from steam compressors to 10TK-2A, 10TK-2B | - From BL18 on steam pipeline 200-SSL-L-192-HC-N to steam compressors including sample point for analyses, analyser QT-10TK-3 and instruments FT-3212, PT-2240, TE-1240 | - 18 | - For details see attachment#1 |
| 12.13 | v. L-195, steam from SRU-2 to ARU-4 | - From BL19 on steam pipeline 200-SSL-L-195-HC-N to BL31 on steam pipeline 200-LS-9060-MS11-HC-N | - 19, 31 | - For details see attachment#1 |
| 12.14 | v. G-4-1-1, steam from LP steam header to evaporator TK-13 | - From BL25 on steam pipeline 250-SSL-G-4-1-1-HC-N to process gas pipeline 20”-HS-A-3-1-1-HC-N | - 25 | - For details see attachment#1 |
| 12.15 | v. G-4-1-1, steam from LP steam header to evaporator TK-14 | - From BL26 on steam pipeline 250-SSL-G-4-1-1-HC-N to process gas pipeline 20”-HS-A-3-1-2-HC-N | - 26 | - For details see attachment#1 |
| 12.16 | v. L-192, steam from LP steam header to evaporator TK-14 | - From BL27 on steam pipeline 200-SSL-L-192-HC-N to process gas pipeline 20”-HS-L-10-3-1-HC-N | - 27 | - For details see attachment#1 |
| 12.17 | v. S-11-1-1, v. S-3-5-3, v. S-3-5-4, blowdown water from evaporators TK-13 & TK-14 to water cooler AV-9 | - From BL5 on water pipeline 100-WBB-S-11-1-1-N-N to evaporator TK-13 & TK-14 including sample points for analyses, instruments FT-3004, FT-3120, TE-1000, TE-1109, PI-2003, PI-2132 and other related equipment & instruments according to the new Detail Design | - 5 | - For details see attachment#1 |
| 12.18 | v. L-211, v. L-210, blowdown water from evaporator 10TK-3 to water cooler 20AV-6 | - From BL22 on water pipeline 800-WBB-L-211-N-N to evaporator 10TK-3 including sample point for analyses, instruments FT-3213, TE-1240, PI-2444 and other related equipment & instruments according to the new Detail Design | - 22 | - For details see attachment#1 |
| 12.19 | v. K-4-1-3, steam condensate from MVR K-1 steam compression system to tank T-11 | - From BL32 on steam condensate tank T-11 to MVR K-1 steam compression system | - 32 | - For details see attachment#1 |
| 12.20 | v. K-4-1-4, steam condensate from MVR K-2 steam compression system to tank T-12 | - From BL33 on steam condensate tank T-12 to MVR K-2 steam compression system | - 33 | - For details see attachment#1 |
| 12.21 | v. L-209, steam condensate from MVR 10K-1 steam compression system to tank 10T-11 | - From BL21 on steam condensate pipeline 50-SCL-L-209-HC-N to MVR 10K-1 steam compression system | - 21 | - For details see attachment#1 |
| 12.22 | v. S-3-1-1, demi water from header to steam compression systems MVR K-1 & MVR K-2 | - From BL23 on demineralized water pipeline 80-DW-S-3-1-1-HC-N to steam compression systems MVR K-1 & K-2 | - 23 | - For details see attachment#1 |
| 12.23 | v. L-10-21, demi water from header to steam compression system MVR 10K-1 | - From BL24 on demineralized water pipeline 80-DW-L-10-21-HC-WT to steam compression system 10MVR K-1 | - 24 | - For details see attachment#1 |
| 12.24 | v. A-2-16-1, process gas from evaporator TK-13 to tank T-9 | - From BL28 on process pipeline 50-AM-A-2-16-1-N-N to process gas pipeline 500-HS-A-3-1-1-N-N | - 28 | - For details see attachment#1 |
| 12.25 | v. A-2-16-1, process gas from evaporator TK-14 to tank T-9 | - From BL29 on process pipeline 50-AM-A-2-16-1-N-N to process gas pipeline 500-HS-A-3-1-2-N-N | - 29 | - For details see attachment#1 |
| 12.26 | v. L-10-3-1, process gas from evaporator 10TK-3 to tank 10T-8 | - From BL30 on process pipeline 25-AM-L-10-22-2-N-N to process gas pipeline 500-HS-L-10-3-1-N-N | - 30 | - For details see attachment#1 |
| 12.27 | Low pressure nitrogen connections | - Low pressure nitrogen is available and all necessary connections is within CONTRACTORS Scope of Works. Tie-in points will be specified during detail design. CONTRACTOR should provide required amount of low pressure nitrogen. | - CONTRACTOR’s Scope of WORKS | - For details see attachments#1, 2, 3, 4. |
| 12.28 | Plant air | - Plant air is available and all necessary connections is within CONTRACTORS Scope of Works. Tie-in points will be specified during detail design. CONTRACTOR should provide required amount of plant air. | - CONTRACTOR’s Scope of WORKS | - For details see attachments#1, 2, 3, 4. |
| 12.29 | Instrument air | - Instrument air is available and all necessary connections is within CONTRACTORS Scope of Works. Tie-in points will be specified during detail design. CONTRACTOR should provide required amount of instrument air. | - CONTRACTOR’s Scope of WORKS | - For details see attachments#1, 2, 3, 4. |
| 12.30 | Cooling water | - Cooling water is available and all necessary connections is within CONTRACTORS Scope of Works. Tie-in points will be specified during detail design. CONTRACTOR should provide required amount of cooling water. | - CONTRACTOR’s Scope of WORKS | - For details see attachments#1, 2, 3, 4. |
| - Civil part |  |  |  |  |
| 13 | Foundation / Paving | - Within CONTRACTOR’s Scope of WORKS including update of topographical map (SRU-1, SRU-2 & cable trestle), geological survey (under containers for steam compression systems & module substation(s)), foundations for evaporators TK-13, TK-14 & 10TK-3, steam compressors containers, substation(s), steel support structures, stairs, ladders and other minor foundations (excavations, foundations, dewatering, paving, etc.,) as well as related anchor bolts. Paving of the entire project area (concrete site under the new evaporators TK-13, TK-14 and 10TK-3, steam compressors, transformer substations, etc.). - The Contractor must independently foresee all the necessary work, if they are not foreseen in the Customer's task, but are necessary for the installed devices to function properly and safely in the existing environment. | - CONTRACTOR’s Scope of WORKS | - For details see attachments#1, 2, 3, 4. |
| 14 | Sewage | - Within CONTRACTOR’s Scope of WORKS including design and execution of required changes of the underground networks (water supply, sewers) considering the selected installation location | - CONTRACTOR’s Scope of WORKS | - For details see attachments#1, 2, 3, 4. |
| 15 | Buildings / containers for steam compression systems | - Within CONTRACTOR’s Scope of WORKS including engineering, design, manufacturing, delivery, installation | - CONTRACTOR’s Scope of WORKS | - For details see attachments#1, 2, 3, 4. |
| 16 | Painting / Coating | - Within CONTRACTOR’s Scope of WORKS including evaporators, containers, process and utility piping, steel structures, platforms, stairs and ladders | - CONTRACTOR’s Scope of WORKS |  |
| 17 | Marking / Labelling / Signing | - Within CONTRACTOR’s Scope of WORKS including pipelines marking according to OL BDS-41 requirements, labels and signs (plastic or aluminium) of all Project equipment | - CONTRACTOR’s Scope of WORKS |  |
| 18 | Hot deep galvanizing | - Within CONTRACTOR’s Scope of WORKS including platforms and ladders and stairs grids and hand rails | - CONTRACTOR’s Scope of WORKS |  |
| 19 | Fireproofing | - Within CONTRACTOR’s scope of WORKS including all support steel structures which shall be fireproofed as per API and ORLEN Lietuva Technical Specification requirements. | - CONTRACTOR’s Scope of WORKS |  |
| - Instrumentation part (for details see attachment No.2) |  |  |  |  |
| 20 | Instrumentation | - All devices, including field devices, temperature measurement instruments, pressure measurement devices, differential pressure measuring devices, flow measurement devices, mass flow rate meters, analyzers, level transmitters, level switches, control valves, shut-off valves, air coolers instrumentation, MVR compressors instrumentation, I/P positioners, filters / reducers, instrument cabinets, electrical heating, conduits, junction boxes, TOP-BOX panel, cables, cable trays / routes related new equipment are included in CONTRACTOR’s Scope of Works. | - CONTRACTOR’s Scope of WORKS | - For details see attachment#2 |
| 21 | Control system (DCS, ESD) | - New signals for readings, alarms and controls shall be that connected to the DCS (Foxboro) system. Tripping signals to be connected to the ESD (Triconex) system. Instrument readings, alarms and control shall be connected to SRU-2 DCS SCADA system and PI server. Installation of new DCS I/O cabinets with redundant power supply and connection cables, installation of new ESD modules and Triconex chassis for I/O modules, redundant power supply and connection cables. All cabinets shall be closed-cooled, supplied with instrumentation air to maintain positive pressure and connected to the existing aspirating smoke detection system in the DCS/ESD cabinets. All that is included in CONTRACTOR’s Scope of Works. | - CONTRACTOR’s Scope of WORKS | - For details see attachment#2,3 |
| 22 | Control system documentation | - Below listed documents shall be prepared by CONTRACTOR and submitted to OWNER: - TAG list - equipment layout plans - installation/functional diagrams - basic wiring diagrams - installation diagrams - basic measuring diagrams (loop drawings) - new equipment selection and intrinsically safe circuit testing calculations - instrument and equipment hookup diagrams - 24 V DC power supply diagrams - cable routes and cable tag drawings - explanatory note, etc. | - CONTRACTOR’s Scope of WORKS | - For details see attachment#3 |
| - Electrical works (for details see attachment No.3) |  |  |  |  |
| 23 | Substation(s)for MVR electrical equipment connection | - Within CONTRACTOR’s Scope of WORKS including engineering, design, manufacturing, delivery, installation, electric equipment connection to substation |  | - For details see attachment#3 |
| 24 | Cables from substation TP-110/6kV “Juodeikiai” to new substation(s) | - The Battery limit includes engineering, design, manufacturing, delivery, installation of electric cables from substation TP-110/6kV “Juodeikiai” to new substation(s). Also within CONTRACTOR’s Scope of WORKS are included calculation and assessment of existing cable trestle loads if the existing cable trestle is not suitable for the installation of a new cable, then a new cable trestle must be installed and the new cable installed in it. |  | - For details see attachment#3 |
| 25 | Electric motors for air coolers AO-1A, AO-1C, AO-2, 10AO-2B, 10AO-2D | - The Battery limit includes engineering, design, manufacturing, delivery, installation and connection of new electric motors, VFD’s for air coolers AO-1A, AO-1C, AO-2, 10AO-2B, 10AO-2C |  | - For details see attachment#3 |
| 26 | Electrical equipment | - All electrical equipment including illumination, electrical heating and heat tracing (if any), grounding, lightning protection, cable routes and cabling up to power cabinets in MCC, power cabinets and secondary equipment (power switches, circuit-breakers, relays and etc.) are included in CONTRACTOR’s scope of WORKS. | - CONTRACTOR’s Scope of WORKS | - For details see attachment#3 |
| 27 | Driver feeding | - Air coolers AO-1A, AO-1C, AO-2 power supply connection from the existing substation TP-16 JVS-3, air coolers 10AO-2B and 10AO-2C power supply connection from the existing substation TP-74 and steam compressors and auxiliary equipment power supply connection from the new transformer substation(s) | - CONTRACTOR’s Scope of WORKS | - For details see attachment#3 |
| 28 | Illumination | - Illumination must be installed in MVR, substation(s) buildings. In new or renewed equipment service points illumination shall be installed if necessary. | - CONTRACTOR’s Scope of WORKS | - For details see attachment#3 |
| 29 | Heat tracing | - Heat tracing installation shall be implement according process, instrumentation or others design part requests. | - CONTRACTOR’s Scope of WORKS | - For details see attachment#3 |
| 30 | Grounding | - Grounding shall be implement according local requirements, civil, mechanical and others design part requests. | - CONTRACTOR’s Scope of WORKS | - For details see attachment#3 |
| 31 | Lightning protection | - Evaluate existing lightning protection. Install new lightning protection if needed. | - CONTRACTOR’s Scope of WORKS | - For details see attachment#3 |
| - Miscellaneous |  |  |  |  |
| 32 | Inspection and testing | CONTRACTOR shall perform all the WORKS specified in the present SOW including all the required on-site testing of all pipelines, pressure equipment, rotary equipment. Testing shall be based on applicable design norms and / or relevant local regulations. The CONTRACTOR’s SOW shall also include coordination of the on-site inspections and other works that require permits to be issued by the local authorities. As well CONTRACTOR is responsible for antifreeze media for hydro tests (if applicable). - NOTE: Expenses arising from inspections and testing of CONTRACTOR performed work by the local authorities are deemed to be included in CONTRACTOR’s Scope of WORKS | - CONTRACTOR’s Scope of WORKS | - Scope of Works |
| 33 | Blinding | CONTRACTOR shall perform all blinding installation and blinding removal activities required for pipelines and pressure equipment installation | - CONTRACTOR’s Scope of WORKS | - For details see attachment#1 |
| 34 | Commissioning & Start-Up | - Assistance as well as defects elimination during Commissioning & Start-Up period is included in CONTRACTOR’s Scope of WORKS | - CONTRACTOR’s Scope of WORKS |  |
| 35 | Performance Test | - Assistance as well as defects elimination during Performance Test period is included in CONTRACTOR’s scope of WORKS | - CONTRACTOR’s Scope of WORKS |  |

- 1.6	BASIC INFORMATION

1.6.1 SITE INFORMATION. All site information data defined in documents listed in paragraph No.1.7;

1.6.2 BASIC INFORMATION PROVIDED BY OWNER. All basic information provided by OWNER data defined in documents listed in paragraph No.1.7;

1.6.3 CODES AND STANDARDS. The codes and standards applicable for WORKS are defined in documents listed in paragraph No.1.7. The EQUIPMENT and MATERIAL shall be strictly in accordance with the requirements imposed by this document and the other documents attached to the Scope of WORKS. In case of conflicting requirements between the different applicable documents, the precedence shall be as follows:

- Code/authority regulations;

- Industrial standards referred to in above-mentioned documents;

- Material requisition, including data sheets.

CONTRACTOR shall report in writing any conflicting requirements to OWNER. It shall be CONTRACTOR’s responsibility to acquire possession of all required regulations, codes and standards.

- The CONTRACTOR is aware of any legal regulation applicable to the subject EQUIPMENT and is solely responsible for full compliance with such rules, including approvals, tests, certificates and services of a legal inspection body.

- 1.7	LIST OF ATTACHMENTS

| Attachment No | Description |
| --- | --- |
| 1 | Technological design proposal OLPP115 |
| 1.1 | OLPP115 List of documents |
| 1.2 | OLPP115 Explanatory note |
| 1.3 | OLPP115 Line list |
| 1.4 | OLPP115 Tie-in list |
| 1.5 | OLPP115 SRU-1 List of Instrumentation Design Tasks |
| 1.6 | OLPP115 SRU-1 Instrumentation Design Task |
| 1.7 | OLPP115 SRU-2 List of Instrumentation Design Tasks |
| 1.8 | OLPP115 SRU-2 Instrumentation Design Task |
| 1.9 | OLPP115-PID-SGI1-13 |
| 1.10 | OLPP115-PID-SGI1-16 |
| 1.11 | OLPP115-PID-SGI1-23 |
| 1.12 | OLPP115-PID-SGI1-24 |
| 1.13 | OLPP115-PID-SGI1-25 |
| 1.14 | OLPP115-PID-SGI1-52 |
| 1.15 | OLPP115-PID-SGI1-53 |
| 1.16 | OLPP115-PID-SGI1-54 |
| 1.17 | OLPP115-PID-SGI1-55 |
| 1.18 | OLPP115-PID-SGI1-56 |
| 1.19 | OLPP115-PID-SGI1-57 |
| 1.20 | OLPP115-PID-SGI1-60 |
| 1.21 | OLPP115-PID-SGI1-61 |
| 1.22 | OLPP115-PID-SGI2-09 |
| 1.23 | OLPP115-PID-SGI2-10 |
| 1.24 | OLPP115-PID-SGI2-19 |
| 1.25 | OLPP115-PID-SGI2-21 |
| 1.26 | OLPP115-PID-SGI2-46 |
| 1.27 | OLPP115-PID-SGI2-48 |
| 1.28 | OLPP115-PID-SGI2-51 |
| 1.29 | OLPP115-PID-SGI2-54 |
| 1.30 | OLPP115-PID-SGI2-56 |
| 1.31 | OLPP115-PID-ARU4-0013-001 |
| 1.32 | OLPP115 Specification sheet for TK-13 |
| 1.33 | OLPP115 Specification sheet for TK-14 |
| 1.34 | OLPP115 Specification sheet for 10TK-3 |
| 1.35 | OLPP115 Specification sheet for QT-TK-13 |
| 1.36 | OLPP115 Specification sheet for QT-TK-14 |
| 1.37 | OLPP115 Specification sheet for QT-10TK-3 |
| 1.38 | OLPP115 Topographic map of SRU |
| 1.39 | OLPP115 SRU ATEX |
| 1.40 | OLPP115 Blinding schemes |
| 1.41 | SGĮ MVR 6kV planas |
| 2 | OLP02632 Instrument Design SOW |
| 2.1 | OL technical requirements from Electrical and Automation Department |
| 2.2 | OL electrical equipment tagging (abbreviations) |
| 2.3 | Requirements for control cables |
| 2.4 | Handover of DD |
| 2.5 | Design registration card |
| 2.6 | Existing desgin drawings |
| 2.7 | Vendor list |
| 2.8 | Current SRU ACS architecture |
| 2.9 | Cause and Effect Matrix - example |
| 2.10 | Instrument Tag List - example |
| 3 | OLP02632 Electrical Design SOW |
| 3.1 | List of Design documents (P_4_1) |
| 3.2 | Electric cable line coding system (P_4_2) |
| 3.3 | List of abbreviations (P_4_3) |
| 3.4 | Harmonized cable coding table (P_4_4) |
| 3.5 | Vendor list (P_4_5) |
| 3.6 | List of technical specifications (P_4_6) |
| 3.7 | Design registration card (P_4_7) |
| 3.8 | Layout plan (P_4_8) |
| 3.9 | TP-74 layout plan (P_4_9) |
| 3.10 | Data sheets for el. motos of air cooler (P_4_10) |
| 3.11 | TP-16 JVS3 single-line diagram (P_4_11) |
| 3.12 | TP-74 JVS1 single-line diagram (P_4_12) |
| 3.13 | Power supply diagrams of designed tranformer houses (P_4_13) |
| 3.14 | AO-1A, AO-1C, AO-2 el. motor control diagram (P_4_14) |
| 3.15 | 10AO-2B el. motor control diagram (P_4_15) |
| 3.16 | 10AO-2C el. motor control diagram (P_4_16) |
| 3.17 | Technical specifications of variable frequency drives (P_4_17) |
| 3.18 | Self-start installation design (P_4_18) |
| 3.19 | Instrumentation Design Task (P_4_19) |
| 4 | ORLEN Lietuva Builder's requirements for designing |

## 2	PARTICULAR REQUIREMENTS

- 2.1	QUALIFICATION REQUIREMENTS FOR CONTRACTOR

- CONTRACTOR shall hold required licenses, certificates as well as other if necessary for execution of design and installation works which in full compliance with Lithuanian requirements;

- CONTRACTOR shall posses certified personnel (welders, installation specialists, supervisors and etc.) to ensure work execution quality;

- WORKS shall be executed by the companies able to work under the flexible work schedule and perform work past working hours, on weekends and public holidays;

- CONTRACTOR shall have an appropriate work experience, possess necessary resources (materials, technical, production, equipment and labor);

- CONTRACTOR shall possess necessary equipment, instruments and other devices for WORKS execution;

- CONTRACTOR shall refer to draft contracts with subcontractors in case WORKS will be executed with involvement of other companies. All subcontractors shall be approved by OWNER;

- Certificates/permits required for Instrumentation installation works. To have necessary permits, certificates granting the right to perform works of such scope according to the requirements of normative acts of the Republic of Lithuania:

  - Operation of special power installations;

  - Operation of electric installations of up to 1000V;

  - Operation of power network and units of up to 1000V;

  - Testing of power network and units of up to 1000V;

  - Installation of process control and automation systems;

  - Operation of automation and control systems of crude oil and/or petroleum product processing (except for liquefied petroleum gas) as well as other liquid fuel refining Units;

- Certificates/permits required for Electrical installation works. A certificate issued by the National Energy Regulatory Council of the Republic of Lithuania entitling to operate electrical units and to perform the following activities:

  - Operation of special power installations;

  - Electrical engineering works up to 10kV;

  - Works related to operation of electrical network and units under voltage up to 10kV;

  - Testing works of electrical network and units, voltage up to 10kV;

  - Operation works of electrical network relay protection, voltage up to 10 kV;

  - Pre-Commissioning of engineering systems of a structure;

- Certificate issued by Ministry of Environment of the Republic of Lithuania, entitling to hold a position of Special Construction Special Civil Work Manager and Special Construction Special Civil Work Technical Supervision Manager (field of activity – electrical units up to 10 kV);

- Qualification requirements for Mechanical/Civil Installation works:

- Certificate issued by the National Energy Regulatory Council (NERC) to operate crude oil processing and petroleum products producing units - a right to do business related to operation of crude oil and petroleum product units. Repair of crude oil processing units irrespective of their parameters;

- Information about company welders‘ qualification, documents confirming welding qualification in accordance with EN287 or EN287+PED welding process 141 and 111, for steel group 1, piping diameter from 20 mm and ≥ 25mm, wall thickness from 3mm to 12 mm;

- Company fusion welding quality certificate according to ISO 3834-2 or ISO 3834-3;

- Company employees that have employment contracts and are certified European Welding Engineer or European Welding Technologist (IWE, EWE or IWT, EWT);

- CONTRACTOR must be insured as stipulated in legislation applied in the Republic of Lithuania;

- CONTRACTOR shall provide a list of SUBCONTRACTORS (if any) and their certificates granting the right to perform such works according to the requirements of the normative acts of the Republic of Lithuania;

- CONTRACTOR shall provide any other certificates/licenses/permits if applicable.

2.2              DOCUMENTATION

CONTRACTOR shall execute the following works, including but not limited to:

- All CONTRACTOR documents shall be in English and Lithuanian languages except to the extent expressly stated otherwise elsewhere in contract;

- The CONTRACTOR shall prepare / translate/ provide:

a). Operation and Maintenance Manual manuals for all newly provided equipment (in English and / or Lithuanian);

b). Operation Manual for operators (in Lithuanian);

c). In addition to Operation and Maintenance Manuals for all newly provided equipment, CONTRACTOR shall prepare / translate / provide a special summary Operation and Maintenance Manuals for all newly installed complicated electrical equipment as UPS, Motors Self-Restart Cabinets, Intermediate panels and etc. (in Lithuanian);

NOTE: An example of above said special summary OMM could be provided by OWNER.

- After WORKS completion, Contractor shall submit respective maintenance documentation, and develop technical certificates (passports). While drafting new piping installation documents, pipeline technical passport, diagram and specifications must be issued following the requirements of Company procedure BM-4 “Safe Operation of Pressure Piping” (available on ORLEN Lietuva website http://www.orlenlietuva.lt/EN/ForBusiness). The electronic version of piping technical certificate (passport), diagram and specifications shall also be submitted to OWNER’s Technical Supervision Shop;

NOTE: New pipeline installation documentation should be issued for all pipelines within the Scope of WORKS (ISBL and OSBL);

- If required, CONTRACTOR shall coordinate and combine works with those performed by third parties;

- CONTRACTOR shall perform all the WORKS specified in the present SOW including all the required on-site testing of all pipelines. Testing shall be based on applicable design norms and/or relevant local regulations. The CONTRACTOR SOW shall also include coordination of the on-site inspections and other works that require permits to be issued by the local authorities;

NOTE: Expenses arising from inspections and testing of CONTRACTOR performed work by the local authorities are deemed to be included in CONTRACTOR’s SOW.

2.3              MANUFACTURING REQUIREMENTS

- All manufacturing requirements are defined in the documents listed in paragraph No. 1.7;

2.4              PAINTING

- All painting requirements are defined in the documents listed in paragraph No. 1.7;

- Marking of Pipelines, vessels, steel structures and etc., shall be implemented according to OL BDS-41 instruction requirements.

2.5              WELDING

The CONTRACTOR shall develop and prepare Welding Procedure Specification (WPS), Welding Procedure Approval Record (WPAR) and Welders Qualification Record (WQR) for all welds. These procedures shall be submitted to the OWNER for review, prior to fabrication. All welders shall be qualified and certified in line with EN 287. All welds on pressure parts (inside as well as outside) shall be fully penetrated. Only material of the same chemical composition, as the base material, can be welded to the pressure retaining parts.

2.6              NOZZLE CONNECTION

All nozzle flanges shall be according to ASME B16.5. Bore of WN flanges shall correspond with the inside diameter of the nozzle necks. All blinded nozzles shall be delivered with blind flange, gasket (spiral wound, inner and outer ring) and bolting. The smallest outside nozzle diameter on shell is 50mm. For smaller nozzles shall be used only LWN flanges.

2.7              MATERIALS AND EQUIPMENT

- All materials and equipment shall comply with ORLEN Lietuva Technical specification, Design data sheets and other documents attached to the requisition. All pressure retaining parts shall be made from material, which shall have material certificate 3.1 according to EN10204. The certificates 3.1 shall be supplied also for welding consumables. Other parts can have material certificates 2.2 as per EN10204.

- All provided equipment and materials shall have necessary certificates and quality control documents (specified in technical requirements);

- Prior to procurement of all materials and/or equipment necessary for the project execution CONTRACTOR shall submit to the OWNER technical data of these materials and/or equipment for inspection and determination of suitability. All materials and/or equipment shall be procured only after OWNER’s approval and after OWNER’s confirmation that the materials and/or equipment are suitable for use and can be installed;

NOTE: Notwithstanding OWNER’s confirmation on suitability of above mentioned goods (based on approved data sheets and/or characteristics), all materials / equipment / service shall be deemed as accepted by OWNER only after successfully performed Start-Up of the Unit;

- CONTRACTOR shall provide all the equipment, installation parts, elements and materials regardless whether they are specified or not in material list, but necessary for the execution of the project, for example, fastening straps, screws, nuts, nozzles, cable seals, markings, paint, etc.;

- CONTRACTOR shall deliver all materials and / or equipment necessary for project execution by its own transport to installation or temporary storage area and ensure material protection against damage, theft or other events;

- The supplied production / equipment / materials shall not be used previously (brand new), shall be produced not earlier than in 2024 and proposal shall contain quality confirming documents (equipment passports, certificates of materials and etc.);

- All materials and equipment shall be manufactured only by vendors listed in ORLEN Lietuva Vendor List except as otherwise expressly provided elsewhere in this CONTRACT.

2.8              NAMEPLATE

The PED / CE marking nameplate shall be made from stainless steel and shall be permanently attached to the nameplate brackets. The nameplate shall be in Lithuanian/English language. The nameplate shall display all data as per PED directive and moreover equipment number and name.

2.9              INSPECTION AND TESTING

Inspection and testing shall be in accordance with the requirements of this requisition and the codes and standards named herein. The minimum inspection and testing requirements in the manufacturer’s workshop as well as at site will be summarized in the Inspection Specification sheet (shall be agreed during Kick-Off meeting). Notified Body approval as per PED 2014/68/EU is required for the equipment and the Seller is responsible to fulfil requirements and actions necessary to obtain the approval. CONTRACTOR shall notify OWNER not less than 10 working days prior to any inspection, witnessed test or hold point. Acceptance of shop test shall not constitute any waiver of field test requirements in order to meet the specified operating conditions, nor does inspection relieve the Seller of his responsibilities in anyway. Duration of hydro test shall not be less than 1 hour. Manufacturer shall indicate on assembly drawing places, where periodical thickness measurement will be performed. The first thickness measurement shall be performed by the manufacturer and shall be included into NDE report.

2.10            TRAINING

The Contractor shall conduct training courses as follows:

2.9.1 On-site operators training. The training shall be organized for 5 different operators groups, which are working based on different shifts;

2.9.2 On-site Electrical / Instrument maintenance personnel training. The training shall be organized for 5 different personnel’ groups, which are working based on different shifts;

2.9.3 Training for service / maintenance personnel in the certificate training centre. Exact training model will be identified during Kick-Off meeting;

2.11           ESTIMATION AND SCHEDULE

CONTRACTOR shall perform the WORKS according to the Time Schedule approved by the OWNER;

CONTRACTOR shall be responsible for development of Project schedule, reporting on WORKS, forecasting and supervision thereof. CONTRACTOR shall plan and provide adequate personnel to ensure completion of WORKS in accordance with the approved Time Schedule.

All tie ins and connections to existing equipment and pipelines will only be possible in spring 2027, during the Refinery Overhaul.

The exact date will be confirmed later, 2 month before shutdown.

Commencement of works – immediately after contract signature;

The OWNER reserves the right to modify the WORKS execution terms in accordance with the Time Schedule.

3     SCOPE OF WORKS

3.1              PROJECT MANAGEMENT AND SITE SUPERVISION

CONTRACTOR shall provide the following services:

3.1.1 Overall project management including planning, procurement, expediting, cost control, QA/QC and the like;

3.1.2 Sufficient personnel for the supervision of the execution of the WORKS including construction management, field supervision, safety management, QA/QC (at site) and the like;

3.1.3 Approvals of Notified Bodies governing the fabrication for the CE Mark;

3.1.4 Fabrication supervisor and/or technical specialist witnessing the fabrication process;

3.1.5 Quality control program and documentary support of manufacturing of goods;

3.1.6 QA/QC over all welding activities;

3.1.7 QA/QC over the applied application of insulation, paint and coatings;

3.1.8 Site technical services for supervision and quality control over the erection of all disciplines (Civil, Mechanical, Instrument and Electrical);

3.1.9 Site technical services for Pre-Commissioning, Commissioning and Start-Up;

3.1.10 Site technical services for other required operational support to assure safe and effective start-up.

3.2              ENGINEERING

CONTRACTOR shall perform all design and detailed engineering required for the WORKS as defined in the CONTRACT. CONTRACTOR’S scope of WORKS for detailed engineering is further defined in present Scope of WORKS and in documents listed in paragraph No. 1.7. CONTRACTOR shall provide the following services, as a minimum, in respect of all engineering disciplines during engineering of the facilities. CONTRACTOR’s engineering scope of WORK shall include but not be limited to:

3.2.1 P&ID:

3.2.1.1 P&ID preparation and issue to OWNER for approval;

      - P&ID modification based on HAZOP Study and SIL determination recommendation;

3.2.2 HAZOP. HAZOP study and SIL classifications shall be conducted by CONTRACTOR in accordance with procedures proposed by CONTRACTOR, for approval by OWNER, covering at least the following stages:

3.2.2.1 HAZOP Review. Prior to final release of P&ID’s, Plot Plans and related documents for Detailed Design, carry out a detailed HAZOP Review; carry out safety reviews of any and all subsequent proposed changes to P&ID’s;

3.2.2.2 Follow-up HAZOP - Conduct HAZOP of Vendor Package P&ID’s, once these are approved;

3.2.2.3 Perform a SIL determination / classification / verification, SRS, Risk Assessment (Layer of Protection Analysis) for determining the characteristics of a Safety Instrumented System (SIS);

3.2.2.4 CONTRACTOR shall fully support the OWNER during HAZOP study to improve the safety, quality and conformity of the WORKS;

3.2.2.5 In case additional equipment (pipes, fittings, isolation valves, instruments, cables, control and/or On/Off valves and etc.) after HAZOP study will be determined, CONTRACTOR shall update P&ID and Detail Design and implement WORKS accordingly;

3.2.3 Geodetic surveys and development of topographic plans;

3.2.4 3D model of new evaporators TK-13, TK-14, 10TK-3, steam compressors including existing equipment K-1, K-2, 10K-1 AO-1/A, B, C, D, AO-2, AO-3, 10AO-2A, B, C, D and pipelines;

3.2.5 Process and mechanical design of the new MVR systems fully equipped as per worldwide best practice based on present Scope of WORKS, data defined in the documents listed in paragraph No.1.7 and Battery Limits listed in paragraph No.1.5 including evaporators for steam production, steam compression systems, transfer and utility pipelines, stairs, ladders and handrails, control valves, isolation and on/off valves, safety and relief valves. Regardless of the load of the columns K-1, K-2 and 10K-1 it must be possible to control the load of new steam compression systems within the range of 20-100 % (indicated control range is not final and may be changed according to the manufacturer’s equipment specifications and upon agreement with the OWNER);

3.2.6 Civil design of the new Fired Heater KR-203 based on present Scope of WORKS, data defined in the documents listed in paragraph No.1.7 and Battery Limits listed in paragraph No.1.5 including foundations for evaporators TK-13, TK-14 and 10TK-3, containers (for steam compression systems), module transformer substation(s), steel support structures, stairs, ladders and other minor foundations, foundations loads, underground networks (water supply, sewers), refractory and and anchoring system, lining, painting, coating, marking, labelling, signing, hot deep galvanizing, fireproofing, fire extinguishers with boxes (10 pcs.), paving of all Project area (concrete yard under all new equipment).

Attachment 1 (1.3 Plot Plan) shows the possible locations of the new equipment and facilities.

The Contractor will need to consider, when preparing the detailed design, that

some areas are shown on top of existing grassland and drainage ditches.

The ditches will need to be laid with drainage pipes, sanded and concreted.

For the construction of the facility, the Customer recommends designing and installing the following coatings:

      - Concrete road paving:

        - Remove the existing concrete paving of ~30 cm thickness;

        - Remove 30 cm of the existing base layer;

        - Install a polyethylene film;

        - Install a cold resistant layer of 20 cm. Ev2 > 120 MPa;

        - Install a rubble base layer of 20 cm. Ev2 > 150 MPa;

        - Install a paving of 24 cm thickness from C30/37 compressive strength class concrete. Install a rebar grid framework, d12, 20x20 cm. Contractor shall consider the installation of construction and expansion joints;

        - Concrete surface finishing (leveling only);

      - Concrete paving for pedestrians:

        - Remove the existing concrete paving of ~30 cm thickness;

        - Remove 20 cm of the existing base layer;

        - Install a polyethylene film;

        - Install a cold resistant layer of 40 cm. Ev2 > 120 MPa;

        - Install a paving of 10 cm thickness from C30/37 compressive strength class concrete. Installing a rebar grid, d10, 20x20 cm. Contractor shall consider the installation of construction and expansion joints;

        - Concrete surface finishing (leveling only);

3.2.7 Instrument design of the new MVR systems based on present Scope of WORKS, data defined in the documents listed in paragraph No.1.7 and Battery Limits listed in paragraph No.1.5 including field devices, temperature measurement instruments, pressure measurement devices, differential pressure measuring devices, flow measurement devices, mass flow rate meters, analyzers, level transmitters, level switches, control valves, shut-off valves, air coolers instrumentation, MVR compressors instrumentation, I/P positioners, filters / reducers, instrument cabinets, electrical heating, conduits, junction boxes, TOP-BOX panel, cables, cable trays / routes. Design shall include Cause & Effect Matrix, field instrument specifications, calculations, take-off, hook-up drawings, cable tray layout drawings, junction boxes drawings, wiring diagrams, material specifications, operating and maintenance manuals, and etc.;

3.2.8 Electrical design of the new MVR systems based on present Scope of WORKS, data defined in the documents listed in paragraph No.1.7 and Battery Limits listed in paragraph No.1.5 including illumination (work and emergency), lightning protection, grounding system, driver feeding, heat tracing (for instrumentation sample piping and process pipelines from freezing where necessary), cable routes and cabling up to power cabinets in MCC, conduits, power cabinets and secondary equipment (power switches, circuit-breakers, relays and etc.), power supply (for illumination, heat tracing, welding panels), junction boxes. Design shall include one line diagrams, electrical load summary with tag numbers, description, rated power, voltage and other relevant information, installation details, cable routes layouts, cable lists, operating and maintenance manuals, and etc.;

    - Designs, Specifications and Procedures required for installation purposes;

3.2.10 Fireproofing design of the new containers (for steam compression systems), module substation(s), substations TP-16 JVS3 and TP-74 based on present Scope of WORKS, data defined in the documents listed in paragraph No.1.7 and Battery Limits listed in paragraph No.1.5;

3.2.11 Qualification requirements for designing works:

CONTRACTOR (or Subcontractor) shall have all required certificates and licenses for Designing / Installation activities in the Republic of Lithuania.  Designing shall be performed according to normative documents, standards valid in the Republic of Lithuania and OWNER’s local regulations and technical requirements. Designer shall comply with the following minimum qualification requirements:

- Designer shall have ISO9001 or equivalent quality system;

- Designer shall bear all required certificates and licenses for designing activities in the Republic of Lithuania;

  - Designer shall have all required valid certificates and permits to perform designing of all parts of exceptional significance facilities, relevant to the execution of works provisioned in this Scope of WORKS;

  - Designer specialists, performing designing activities, shall be certified according to the procedure established in the Republic of Lithuania;

  - Designer shall be insured in compliance with the legislation applied in the Republic of Lithuania;

3.2.12 CONTRACTOR’S designated designers team shall present on SITE on constant basis during all engineering phase;

3.2.13 All Detail Design documents shall be submitted to third, certified Experts Company for examination and only after Experts positive conclusion to the OWNER for approval. Only approved by OWNER documents can be issued as “ISSUE FOR CONSTRUCTION” and / or “AS BUILT”. Any construction activities without OWNER’s approval of above said documents are strictly forbidden.

NOTE: Despite OWNER’s confirmation and / or approval of any Detail Design document, all WORKS shall be deemed as accepted by OWNER only after PROVISIONAL ACCEPTANCE CERTIFICATE will be approved by OWNER. Review and approval by OWNER of any CONTRACTOR's Detail Design documents shall not constitute, or be construed as, an assumption of CONTRACTOR's responsibility or liability for Detail Design under the Contract or at law and does not relieve CONTRACTOR from full compliance with its legal and contractual obligations.

3.2.14 Detail Design Identification:

| Detail Design number | OLP02632 |
| --- | --- |
| Detail Design title | SRU K-1, K-2 and 10K-1 waste heat utilization for steam production using mechanical vapor recompression (MVR) technology |

3.3              MATERIAL PROCUREMENT AND SUBCONTRACTING

3.3.1 The CONTRACTOR’s scope of WORKS includes the purchasing, supply, manufacturing, assembling and transportation at site of main Project equipment as:

3.3.1.1 New special type evaporators TK-13, TK-14 and 10TK-3 (process gas / BFW (L.P. saturated steam)) suitable for MVR technology applications, fully equipped as per worldwide best practice including water circulation pumps (if any), junction boxes, cables and cable trays / routes, conduits, instrumentation & electrical equipment, stairs, ladders and handrails, transfer and utility pipelines, control valves, isolation and on/off valves, safety and relief valves, all utility piping, lifting lugs, service platforms, access routes, manholes, painting / coating, thermal insulation, illumination, grounding, anchor bolts and nuts;

3.3.1.2 New steam compression systems for columns K-1, K-2 and 10K-1 fully equipped as per worldwide best practice including steam compressors, compressors lubrication and cooling systems (if necessary), compressors sealing system, gaskets, steam desuperheating system, steam traps for removing condensate between compressors (if necessary), condensate tank and pump (if necessary), VFD’s, junction boxes, cables and cable trays / routes, conduits, instrumentation & electrical equipment, control valves, isolation and on/off valves, safety and relief valves, transfer and utility pipelines, painting, thermal insulation, containers for the new steam compression systems with HVAC and fire protection systems;

3.3.1.3 New module transformer substation(s) fully equipped as per world best practice including new electric cables from TP-110/6 kV "Juodeikiai" transformer substation 6 kV switchgear to new module transformer substation(s);

3.3.1.4 New HVAC system, suction of hot air from VFD’s and fire protection system for existing substation TP-16 JVS3 fully equipped as per worldwide best practice;

3.3.1.5 New air conditioning system, suction of hot air from VFD’s and fire protection system for existing substation TP-74 fully equipped as per worldwide best practice;

3.3.1.6 New electric motors, VFD’s for air coolers AO-1A, AO-1C, AO-2, 10AO-2B, 10AO-2C fully equipped as per worldwide best practise;

3.3.2 The scope of WORKS includes the purchasing, supply and transportation at site of all Mechanical, Civil, Instrument and Electrical equipment and materials as per scope of WORKS and newly prepared and issued Detail Design OLP02632 approved by OWNER and which are necessary for Project execution;

3.3.3 The scope of WORKS includes the purchasing, supply and transportation at site of all equipment and materials required for temporary use as temporary supports, material for blinding, gaskets, bolts, nuts end etc.;

3.3.4 The scope of WORKS includes the purchasing, supply and transportation at site of all Pre – Commissioning, Commissioning and Start-Up spare parts as gaskets, bolts, lubricates and etc.;

3.3.5 The scope of WORKS includes scaffolds, cranes, insulation, any transport, forklifts, special tools or equipment, equipment for cold tie-ins, steam / water / electrical tracing materials, painting materials, labelling materials;

3.3.6 The scope of WORKS includes any additional materials and equipment specified after HAZOP study and SIL verification;

3.3.7 CONTRACTOR shall prepare a Procurement Plan for equipment and materials for OWNER’S review and approval. This Plan shall include a detailed schedule of procurement activities with respect to organizing the project procurement functions and their respective duration for all project materials requirements. This plan shall also be developed in conjunction with CONTRACTOR’S scheduling group for timely and efficient procurement of the equipment and materials. The plan shall define all procurement activities necessary to ensure that all package units, equipment and materials are delivered to the Site by their "Required at Site" dates and that the construction requirements for materials are addressed in the proper sequence to complement planned field construction activities. CONTRACTOR shall submit project specific Procurement Procedures in accordance with OWNER requirements as outlined in the CONTRACT, for OWNER’S approval. CONTRACTOR’S final project-specific Procurement Procedures shall be submitted for review and agreement with OWNER within 4 weeks from the CONTRACT effective date. These Procedures shall set out all interfaces with OWNER and the actions of each Party accordingly;

3.3.9 Plan for sub-contracting shall be prepared by CONTRACTOR for agreement with OWNER, to define the sub-contracting approach to be adopted for the project, including a definition of equipment and materials to be supplied by sub-contractor. OWNER shall only consider requests from CONTRACTOR for approval of additional sub-contractor or in exceptional circumstances;

3.3.10 CONTRACTOR shall perform all expediting of equipment and material, Vendor data, personnel and documentation, from inquiry through to delivery at Site. CONTRACTOR shall submit status reports on all procurement activities. The extent of expediting by CONTRACTOR shall include:

  - Physical expediting at vendor / sub-contractors point of manufacture;

  - Monitoring and reporting progress on all purchase orders and preparing and issuing a listing of critical items at weekly intervals. This listing shall identify those equipment and materials which are critical or are potentially critical to the TIME Schedule and as such require special attention to ensure timely site delivery, along with an action plan to achieve it;

  - CONTRACTOR shall report any unreasonable delay to Procurement Plan that may affect the TIME schedule, stating the reasons for the delay.

CONTRACTOR shall be responsible for ensuring all inspection and for witnessing tests of equipment and materials, at vendor / sub-contractors facilities, in accordance with the requirements of the CONTRACT. Third Party / Authority Inspection (where applicable) shall not relieve the CONTRACTOR of his obligations under the CONTRACT. CONTRACTOR shall prepare an inspection plan for equipment and materials, identifying scope, class and stages of inspection / testing as well as manpower resources from the relevant areas, for carrying out timely stage inspection, final inspection and testing at Vendor/ Sub-contractor’s facilities as required. This plan shall be submitted to OWNER for review. OWNER shall have the right to attend any inspection visits, periodic or final, with a detailed plan and proper notification of all inspections. CONTRACTOR shall be responsible for providing OWNER with a detailed plan and proper notification in this regard;

3.3.11 Prior to procurement of all materials and / or equipment necessary for the project execution CONTRACTOR shall submit to the OWNER technical data of these materials and / or equipment for inspection and determination of suitability. All materials and / or equipment shall be procured only after OWNER’s approval and after OWNER’s confirmation that the materials and / or equipment are suitable for use and can be installed;

NOTE: Despite OWNER’s confirmation on suitability of above mentioned goods (based on approved Data Sheets and / or characteristics), all materials / equipment / service shall be deemed as accepted by OWNER only after PROVISIONAL ACCEPTANCE CERTIFICATE will be approved by OWNER. Review and approval by OWNER of CONTRACTOR's any materials / equipment / service procurement documents shall not constitute, or be construed as, an assumption of CONTRACTOR's responsibility or liability for materials / equipment / service under the Contract or at law and does not relieve CONTRACTOR from full compliance with its legal and contractual obligations;

3.3.12 All materials and equipment shall be manufactured by vendors listed in ORLEN Lietuva Vendors list except for evaporators and steam compression systems where CONTRACTOR can propose other vendors. CONTRACTOR must obtain approval from OWNER for non-listed vendors.

3.4              ERECTION / INSTALLATION

- 3.4.1 Field Services. CONTRACTOR shall provide qualified labour, tools, construction equipment, facilities, direct materials, indirect materials, consumables, supervision, management, technical and professional services and each and every other item necessary for the completion of the Works to achieve issuance of the Final Acceptance Certificate. This section covers the minimum requirements for field services to be executed by CONTRACTOR in accordance with the CONTRACT requirements. The CONTRACTOR’S scope of field services shall include, but not be limited to the following:

- Construction;

- Construction Management;

- Health, Safety and Environmental;

- Field Engineering and Design Supervision;

- Materials Management and Control;

- Planning and Scheduling;

- Project Control / Cost Control;

- Sub-contracts administration;

- Quality Assurance / Control and Management;

- Pre-COMMISSIONING and Commissioning activities;

- Start-Up, Initial Operation and Performance Test;

- Reporting;

- Document and Drawing Control;

- Security;

- Training of OWNER’S personnel. All necessary instructions, maintenance manuals and other documentation must be prepared and approved by OWNER before training.

3.4.2 Project Management and Site Supervision. CONTRACTOR shall provide the following services:

- Overall project management including planning, procurement, expediting, cost control, QA/QC and the like;

- Sufficient personnel for the supervision of the execution of the WORKS including construction management, field supervision, safety management, QA/QC (at site) and the like;

- Approvals of Notified Bodies governing the fabrication for the CE Mark;

- Fabrication supervisor and / or technical specialist witnessing the fabrication process;

- Quality control program and documentary support of manufacturing of goods;

- QA/QC over all welding activities;

- QA/QC over the applied application of insulation installation and painting;

- Site technical services for supervision and quality control over the erection of all disciplines (Civil, Mechanical, Instrument and Electrical);

- Site technical services for Pre-Commissioning, Commissioning and Start-Up;

3.4.3 Civil works. The CONTRACTOR shall provide the necessary activities (pre-assembling and assembling, pre-fabrication and fabrication and installation works), facilities and tools for the erection of all civil works listed in this scope of WORKS, documents listed in paragraph No. 1.7 and newly prepared and issued Detail Design OLP02632 approved by OWNER and which are necessary for Project execution within the Battery Limits determined in article 1.5. CONTRACTOR’S scope of WORKS shall include the excavations, foundations, dewatering, paving, etc.

3.4.4 Mechanical works. The CONTRACTOR’s shall provide the necessary activities (pre-assembling and assembling, pre-fabrication and fabrication, blinding and installation works), facilities and tools for the erection of all mechanical works listed in this scope of WORKS, documents listed in paragraph No. 1.7 and newly prepared and issued Detail Design OLP02632 approved by OWNER and which are necessary for Project execution within the Battery Limits determined in article 1.5. CONTRACTOR’S scope of WORKS shall prepare and submit to OWNER technical certificates (passports) of all Project pressurized equipment and piping based on requirements listed in OL Technical specification;

3.4.5 Instrumentation works. The CONTRACTOR’s shall provide the necessary activities (pre-assembling and assembling, pre-fabrication and fabrication and installation works), facilities and tools for the erection of all instrumentation works listed in this scope of WORKS, documents listed in paragraph No. 1.7 and newly prepared and issued Detail Design OLP02632 approved by OWNER and which are necessary for Project execution within the Battery Limits determined in article 1.5;

3.4.6 Electrical works. The CONTRACTOR’s shall provide the necessary activities (pre-assembling and assembling, pre-fabrication and fabrication and installation works), facilities and tools for the erection of all electrical works listed in this scope of WORKS, documents listed in paragraph No. 1.7 and newly prepared and issued Detail Design OLP02632 approved by OWNER and which are necessary for Project execution within the Battery Limits determined in article 1.5;

3.4.7 CONTRACTOR shall perform all the WORKS specified in the present scope of WORKS including all the required on-site testing of all pipelines, pressurized equipment. Testing shall be based on applicable design norms and / or relevant local regulations. The CONTRACTOR’s scope of WORKS shall also include coordination of the on-site inspections and other works that require permits to be issued by the local authorities;

NOTE: Expenses arising from inspections and testing of CONTRACTOR performed work by the local authorities are deemed to be included in CONTRACTOR’s SOW;

3.4.8 Backfilling and reinstatement of the landscape, grass planting and other miscellaneous work shall be a part of CONTRACTOR’S scope of WORKS;

3.4.9 Provide all other necessary works to reach the targets set above;

- NOTE: CONTRACTOR’S scope of WORKS may not be complete in every detail. The omission of any item shall not relieve the CONTRACTOR of his responsibility to include whatever is necessary to provide a complete and functioning facility.

4     TEMPORARY CONSTRUCTION FACILITIES AND UTILITIES

4.1              Provided by OWNER

OWNER shall furnish, or cause to be furnished, free of charge to CONTRACTOR the following items and / or services for or in connection with performance of the WORKS:

    - Work permits and authority applications (where necessary);

    - Utilities for CONTRACTOR’s temporary facility area and for the execution of the WORKS;

    - Space for CONTRACTOR’s supplied temporary facilities. Any upgrading / paving required for CONTRACTOR’s temporary facilities and working area are for CONTRACTOR’s account;

    - Supply of electrical power for temporary facility needs within approximately 100 meters of CONTRACTOR’s temporary facility area. Any works and materials required for electrical power connection from OWNER’S power distribution panels to CONTRACTOR’S facility area are for CONTRACTOR’s account;

    - Construction and untreated hydrostatic test water, plant air and nitrogen from sources located within approximately 100 meters of the PLANT Battery Limits. Any works and materials required for connection from OWNER’S distribution piping to the PLANT are for CONTRACTOR’s account;

    - Trash containers for solid waste only, and removal of containers from PLANT;

    - Employee identification (I.D.) badges, site access control and vehicles permit. Vehicles permit will be limited to those required for construction activities;

    - Off-site parking facilities;

    - The power supply can be started only after the CONTRACTOR will accomplish the local safety regulation and the deed of responsibility will be signed between OWNER and CONTRACTOR.

4.2              Provided by CONTRACTOR

All construction temporary facilities, utilities, construction equipment and tools, temporary construction materials, consumables, expendables, supplies, fuels, lubricants and any other items, necessary for the complete performance of the WORKS and not listed in Article 3.3 of this scope of WORKS shall be supplied, installed and properly maintained by CONTRACTOR as part of its scope of WORKS;

The type of facilities, move-in and move-out dates and locations on the WORKS site shall be subject to and in accordance with the review and approval of OWNER. Further they shall be in a condition safe and suitable for the intended purpose and in compliance with OWNER’S requirements, the applicable rules and regulations for the WORKS site. OWNER shall have the right to inspect, test and reject any or all temporary facilities and utilities. Rejected temporary facilities and / or utilities shall promptly be removed by CONTRACTOR and replaced with temporary facilities and utilities acceptable to OWNER at CONTRACTOR’S cost, and at no cost to OWNER, and without causing delay to the WORKS.

5     SCHEDULING AND REPORTING

CONTRACTOR is responsible for scheduling, reporting, forecasting and controlling its own activities and shall plan and adequately staff the Project to ensure that the WORKS is completed in accordance with the specific milestones and scheduling requirements listed below:

- Engineering deliverables by discipline;

- Mobilization time for manpower and equipment;

- Start and completion dates of different segments of WORKS;

- Any qualifying conditions of OWNER;

- Other as necessary.

OWNER’S normal working hours are forty (40) hours per week, eight (8) hours per day, five (5) days per week (Monday through Friday), between the hours of 8:00 a.m. and 5:00 p.m.  CONTRACTOR shall submit its schedule of working hours and manpower loading for review and approval by OWNER.

5.1              Reporting

CONTRACTOR shall promptly submit the schedules and reports set forth below and, in addition, those schedules and reports that are requested by OWNER.

5.1.1. A Master bar chart schedule based on the critical path as specified by OWNER;

5.1.2 The activity listing shall show the following information for the main activities shown on the Schedule:

- Identification by code numbers and description;

- Duration;

- Discipline and / or craft;

- Early start and finish dates;

- Latest start and finish dates;

- Total float time and free float time;

    - A detailed WORKS schedule, updated weekly of day-to-day operations showing planned manpower loadings for major activities at site;

    - Major construction equipment correlated to the above detailed work schedule;

    - Safety status report with statistics issued monthly by the 5th day of each month;

    - Procurement schedule for the procurement and receipt of materials, equipment and sub-contract services by CONTRACTOR and a monthly status report of all such procurement, materials and equipment;

    - During the latter stages of accomplishing WORKS, and prior to delivering notice of completion of the WORKS, CONTRACTOR shall submit its plans for demobilization at the WORK SITE to OWNER for approval and shall comply with such demobilization plan as approved by OWNER.

  - Weekly coordination Meetings – Construction Phase

5.2.1 A weekly written report showing actual activities completed versus planned, and scheduled progress versus actual progress. In addition to giving details of WORKS completed in relation to the approved schedule, a one week “look ahead” showing details of how the WORKS will be accomplished in the coming period. Report shall also identify remaining WORKS and estimated hours required to complete such WORKS;

5.2.2 CONTRACTOR shall attend a weekly safety coordination meeting together with various contractors at the WORK SITE;

5.2.3 The person or persons designated by CONTRACTOR to attend the meetings shall have all the required authority to make decisions and commit CONTRACTOR to solutions agreed upon during any coordination meetings;

5.2.4 Starting from construction phase CONTRACTOR’S designated Project Manager as well as Project Engineer shall present on SITE on constant basis.

5.3              Other Meetings

CONTRACTOR participation in certain other activities will be required – they will be coordinated on demand. These activities will include, but not be limited to:

- Project coordination and design review meetings;

- Weekly tool-box safety meetings (during construction phase at site) organized and conducted by CONTRACTOR and attended by all of CONTRACTOR’s craft employees. CONTRACTOR shall be responsible for arranging and conducting these meetings with its craft employees.

6     DATA REQUIREMENTS

  - OWNER’s Data

    - OWNER will issue one copy of OWNER drawings and other technical data for CONTRACTOR’s use. For all other OWNER - supplied documentation, OWNER will provide only one copy of such documentation to CONTRACTOR;

  - CONTRACTOR’s Data. CONTRACTOR shall submit the following data to OWNER as part of the Scope of WORKS:

6.2.1 Two (2) copies of Detail Design version “ISSUE FOR CONSTRUCTION” for all disciplines (print + memory stick (hereinafter stick));

6.2.2 Two (2) final copies of Detail Design version “AS BUILD” after execution of the WORKS (print + stick);

NOTE: After completion of the design works as per contract requirements, the Contractor shall submit design documents, signed and approved, to OWNER’s Project Manager (2 original hard copies and 1 soft copy on a print + stick – drawings in *.pdf, *.dwg, *.doc, *.xls and other original formats); In case of any modifications made to the design during construction (reconstruction, installation), documents must be revised and marked-up. After construction all drawings (with modification or without) marked ‘AS BUILD’ and signed must be issued by Contractor and handed over to the OWNER.

6.2.3 Two (2) final copies of all quality control turnover packages (print + stick);

6.2.4 Two (2) final copies of all test reports and test certificates (print + stick);

6.2.5 Two (2) final copies of mill certificates for all supplied materials (e.g. rebar, plate steel, nozzles and the like) (print + stick);

6.2.6 Two (2) final copies of all piping NDE tests (print + stick);

6.2.7 Two (2) final copies of all welding folders (print + stick);

6.2.8 Two (2) final copies of all welding X-ray reports (print + stick);

6.2.9 Two (2) final copies of all stress relieving reports (print + stick);

6.2.10 Two (2) final copies of all pressure testing documentation (print + stick);

6.2.11 Welding procedures for OWNER’s approval, submitted fifteen (15) working days prior to commencing welding. Alternatively, CONTRACTOR may submit its pre-approved welding procedures for project record purposes to OWNER prior to commencing welding;

6.2.12 Quality Control Program for review and approval prior to commencement of WORKS;

6.2.13 All necessary QA/QC turnover documentation as WORKS or portion thereof is completed;

6.2.14 At completion of WORKS, a complete report of all tests and all reports required by standards and specifications (print + stick);

6.2.15 All lifting and rigging procedures for review and approval prior to lifting or erecting equipment;

6.2.16 Any and all other data requirements to comply with Lithuanian regulatory agencies, inspections and etc.;

6.2.17 CONTRACTOR shall submit all engineering data, (herein called “data”) to OWNER and OWNER designated representatives for review. OWNER shall return data submitted by CONTRACTOR within five (5) working days from transmittal date. No data shall be issued without a transmittal signed by CONTRACTOR or its representative. Data may be issued under one of six (6) separate designations.

    - Preliminary

    - Issued for information

    - Issued for Permit Application

    - Issued for approval

    - Issued for construction

    - As-built

6.2.18 Revisions made to previously issued drawings (either preliminary or issued for approval) shall be identified using alpha (a, b, c) designations. When revising existing drawings the next sequence revision number for that drawing shall be used no matter what the drawing is revised for. Revisions made to “Issued for Construction” will be identified using numeric (0, 1, 2) designations starting with zero (0). Revised areas of submitted drawings and / or text documents are to be clearly identified by clouding (underlining in text documents) with the revision designation shown within a small triangle in that area;

6.2.19 CONTRACTOR shall furnish to OWNER reproducible drawings revised by CONTRACTOR to show “as built” information. CONTRACTOR’s revisions will show details of those locations where the WORKS performed by CONTRACTOR was at variance with the details shown on the drawings (either furnished by OWNER, or furnished by CONTRACTOR and reviewed by OWNER). CONTRACTOR’s submittal to OWNER of such “as built” drawings shall be made on a continuous basis as the WORKS proceeds but in all cases prior to the date of Notice of Acceptance;

6.2.20 OWNER reserves the right to review certified material test reports for all materials of construction at any time during field erection. CONTRACTOR shall maintain these documents readily available for such review and shall submit all documents to OWNER upon completion of the WORKS;

6.2.21 CONTRACTOR shall maintain at the WORK SITE up-to-date copies of all drawings, specifications, and other documents and supplementary data, complete with latest revisions thereto. In addition, CONTRACTOR shall maintain a continuous record of all field changes on the “as built” drawings and other engineering data and shall submit the required number of copies thereof to OWNER;

7     CLEANUP, SAFETY, WORK RULES AND REGULATIONS

# CLEAN-UP

7.1.1 CONTRACTOR shall at all times keep its work area in a neat, clean and safe condition and remove from the OWNER’s premises and the vicinity thereof and properly dispose of all debris and rubbish caused by CONTRACTOR’s operations. Upon completion of the WORKS, CONTRACTOR shall promptly return unused materials furnished by OWNER and remove from OWNER’s premise all of CONTRACTOR’s equipment, material, scaffolding and like items, leaving OWNER’s premises and the vicinity clean, reinstated, safe and ready for use;

7.1.2 In the event CONTRACTOR shall fail to maintain its WORKS area as described above and in a manner satisfactory to OWNER, or to effect such clean-up or removal immediately after receipt of written notice to do so, OWNER shall have the right without further notice to CONTRACTOR to perform such clean-up and remove such items on behalf of, at the risk of and at the expense of CONTRACTOR. OWNER may store items removed at a place of its choosing on behalf of CONTRACTOR and at CONTRACTOR’s risk and expense. OWNER will promptly notify CONTRACTOR of such place of storage. CONTRACTOR shall promptly reimburse OWNER for the costs of such clean-up, removal and storage.

# 7.2 SAFETY

7.2.1 Safety is of prime importance. All contractors and sub-contractors working on the Project shall have in effect a Safety Plan and shall designate a Safety Representative. CONTRACTOR will not receive additional compensation for compliance with safety rules and regulations;

7.2.2 CONTRACTOR's Safety Representative shall be responsible for implementing the CONTRACTOR’s Safety Plan as reviewed by OWNER’s Safety, Health and Environmental (SHE) Manager. CONTRACTOR’s Safety Representative shall ensure that WORKS SITE safety requirements and procedures are being adhered to, conduct safety inspections of work being performed, conduct weekly safety meetings with craft employees and submit a weekly report to OWNER documenting safety activities. The Safety Representative shall also be responsible for a continuing survey of CONTRACTOR’s operations, to ensure that the probable causes of injury or accident are controlled and corrected and that operating equipment, tools and facilities are used, inspected and maintained as required by applicable safety and health regulations;

7.2.3 Technical Product Data Sheets or Material Safety Data Sheets which include health, environmental and safety data or alternatively separate product safety data sheets as issued by the applicable Manufacturer for each product, are to be in the possession of CONTRACTOR and to be kept available at all times during the execution of the WORKS at the WORKS SITE;

7.2.4 SHE Managers, their designated representatives and OWNER shall have the right to stop WORKS whenever safety violations are observed which could jeopardize the well-being of personnel and equipment. The expense of any such WORKS stoppage and resultant standby time shall be to CONTRACTOR's account. The failure or refusal of CONTRACTOR to correct the observed violation may result in the termination of the Contract, and / or the dismissal from the WORKS SITE of those responsible for such failure or refusal;

7.2.5 CONTRACTOR shall provide to OWNER’s SHE Manager a copy of all reports made to government agencies or insurance companies relating to any WORK SITE accident or injury during CONTRACTOR's performance of the WORKS;

# 7.3 WORK Rules and Regulations

7.3.1 CONTRACTOR shall comply with all WORKS rules and regulations set forth in Requirements for Contractors Performing Maintenance-Installation of Process Units at Public Company ORLEN Lietuva. The attachment provided on the website http://www.orlenlietuva.lt/EN/ForBusiness/DocumentsForContractors/Pages/default.aspx;

Prior to work commencement, CONTRACTOR shall develop its Waste Management Plan and get it approved by Project Manager, head of the (sub)division / department / unit where the works are to be performed, and Environmental Department. CONTRACTOR shall clean the work site at the end of each shift, sort the waste generated during the works and remove it to the location indicated by OWNER. In doing this, it shall observe Public Company ORLEN Lietuva Rules on Waste Management.

# 7.4 Hazardous Substances

CONTRACTOR shall comply with applicable hazardous substance disclosure requirements set forth in ORLEN Lietuva website http://www.orlenlietuva.lt/EN/ForBusiness/DocumentsForContractors/Pages/default.aspx;

8     QUALITY PROGRAM REQUIREMENTS

# 8.1             CONTRACTOR’s Quality Plan

CONTRACTOR shall be responsible for the performance of all activities affecting quality including those of its Subcontractors and Vendors. CONTRACTOR's Quality Plan and Inspection and Test Procedures shall be submitted for review and authorization to proceed within forty five (45) days of CONTRACT EFFECTIVE DATE, but not later than fourteen (14) days prior to placement of each main sub-order. The Plan shall specify the controls and documentation procedures that will be employed to assure and document that the CONTRACT requirements are being achieved. Minimum requirements for the quality control effort shall be:

    - The performance of all procedures, checks, inspections, tests, reviews, certifications and other requirements called for in the scope of WORKS, including Specifications, Drawings, Attachments, pertinent codes and other CONTRACT Documents;

    - The preparation of documentation that provides objective evidence of compliance to requirements and the actual performance, in a timely manner, of tests, reviews, certifications, checks, inspections and other verification activities. CONTRACTOR's standard forms may be used in lieu of the documentation forms provided, if agreed by OWNER.

# 8.2             Drawing and Specification Control

CONTRACTOR shall establish a system for the control of design and construction drawings, installation instructions, specifications and other documents used to perform the WORKS. CONTRACTOR shall assign responsibility to guarantee current drawings and documents and changes thereto are available to user(s) and that obsolete documents are retrieved and controlled.

# 8.3             Inspection and Test Status Control

CONTRACTOR shall establish and maintain a system to identify inspection and test status to ensure all inspections, tests and other requirements are accomplished.

# 8.4             Documents & Record Control

CONTRACTOR shall provide and maintain a Document Control System for records of quality control actions of both CONTRACTOR and its subcontractors and vendors. Ensure timely publication and retrieval of all quality records including, but not limited to:

    - Evidence of inspection to assure adherence to applicable drawings, specifications and changes thereto;

    - Test data records of all tests performed. Test data records shall be traceable to acceptably tested material;

    - Non-conformance and corrective action records;

    - Material testing and equipment calibration records and logs;

    - Maintain quality control records ready for OWNER’s inspection;

    - Submit originals of all quality inspection and test documentation as WORKS progresses;

    - All construction quality related activities and procedures.

9     CONSTRUCTION

CONTRACTOR shall provide, institute, and / or implement the following:

# 9.1             Security Program

CONTRACTOR shall be responsible for the security of its workers, tools, materials and equipment on (and in transit to and from) the WORKS site. All small tools and construction equipment belonging to CONTRACTOR shall be clearly identified as such. Tools including personal tools are subject to inspection at the security gate on arrival and departure;

# 9.2             Joint Occupancy

The roads to the WORKS SITE on the refinery will be used jointly by OWNER and other contractors;

# 9.3             Construction Area Limits

OWNER will designate the boundary limits of access roads, parking areas, storage areas, and construction areas. CONTRACTOR shall not trespass in or on areas not so designated. CONTRACTOR shall be responsible for keeping all of its personnel out of areas not designated for CONTRACTOR's use. In the case of isolated WORKS located within such areas, OWNER will issue permits to specific CONTRACTOR’s personnel to enter and perform the WORKS;

# 9.4             Temporary plant roads within CONTRACTOR’s area

The construction area will be constructed and maintained by CONTRACTOR. All roads constructed by CONTRACTOR shall be adequate for applied traffic loads and to prevent damage to underground facilities. All temporary roads are to be removed prior to completion, unless OWNER directs them to be retained;

# 9.5             Restricted roads adjacent to CONTRACTOR’s area

Roads other than those mentioned above are restricted for reasons of safety. CONTRACTOR shall not be permitted access or use of these roads. Restricted roads will be defined when construction arrangements are finalized;

# 9.6             Fence

CONTRACTOR shall install temporary fence 15 meters from the operating zone around CONTRACTOR’s construction area;

# 9.7             CONTRACTOR’s Office at Site of WORK

During the performance of this CONTRACT, CONTRACTOR shall maintain a suitable office at or near the site of the WORKS which shall be the headquarters of a representative authorized to receive drawings, instructions, or other communication or articles. Any communication given to the said representative, or delivered at CONTRACTOR's office at the site of the WORKS in his absence, shall be deemed to have been delivered to CONTRACTOR;

# 9.8             CONTRACTOR’s Temporary Buildings

All temporary construction buildings provided by CONTRACTOR shall be fire retardant.  The location size(s), quantity and types(s) of temporary buildings shall be subject to OWNER’s review and approval;

# 9.9             Clean up

CONTRACTOR shall at all times keep its WORKS area and plant roads in a neat, clean, open and safe condition and remove from the OWNER’s premises and the vicinity thereof and properly dispose of all debris and rubbish caused by CONTRACTOR’s operations;

# Radios on Site

    - Hand held radios sufficient for communications and emergency response may be permitted. Approval for use of radio shall be obtained through OWNER;

    - CONTRACTOR shall obtain any necessary licenses to operate radios on the WORK SITE. Any such radios shall operate on frequencies authorized by OWNER;

# Personnel identification

OWNER will provide ID badges to all CONTRACTOR’s employees working either directly or indirectly under its supervision. Badges must be worn conspicuously by these employees at all times;

# No Smoking

No smoking will be allowed in the work area(s) or outside of the designated smoking areas;

# Personnel Clothing and Equipment

CONTRACTOR’s personnel must wear hard hats clearly marked with employee name, and Company logo. CONTRACTOR shall equip its employees with safety boots, safety glasses and all other safety equipment as required under Lithuanian law and / or by OWNER and such clothing including long sleeved shirts, coveralls, long pants, etc.;

# Dust Control

CONTRACTOR shall, for the duration of the Contract, maintain all excavation, embankments, haul roads, plant sites, waste disposal areas, borrow areas, and all other WORKS areas free from dust, as determined by OWNER. Industry-accepted methods of dust control suitable for the area involved, such as sprinkling, chemical treatment, light bituminous treatment or similar methods, will be permitted. No separate payment will be made for dust control;

# Water Pollution

CONTRACTOR shall, at its expense, provide suitable facilities to prevent the introduction of any substances or materials into any sewer, stream, lake or other body of water which may pollute the water or constitute substances or materials deleterious to fish and wildlife;

# Air Pollution

CONTRACTOR shall so perform the WORKS as not to discharge into the atmosphere from any source whatsoever smoke, dust, or other air contaminants in violation of the laws, rules and regulations of the governmental entities having jurisdiction;

# Ventilation

    - CONTRACTOR shall prevent hazardous accumulations of dust, fumes, mists, vapours or gases in areas occupied during construction;

    - CONTRACTOR shall provide local ventilation to prevent harmful accumulation of hazardous substances into atmosphere of occupied areas;

    - CONTRACTOR shall dispose of materials in a manner that will not result in harmful exposure to persons or disrupt or otherwise effect operation of existing facilities;

    - CONTRACTOR shall ventilate storage spaces containing hazardous, volatile or high temperature sensitive materials;

# SITE Signs

Identification signboards and notices for safety or instruction are permitted on site only after approval of OWNER for format, location and quantity;

# Drainage

CONTRACTOR shall provide proper and adequate drainage for its construction, storage, parking and fabrication areas including the necessary piping for disposal to OWNER ditches, or sewers. Temporary drainage facilities shall be removed upon completion of WORKS unless OWNER directs to have the facilities left in place. CONTRACTOR shall be responsible for providing and operating any temporary pumps for keeping its area drained. CONTRACTOR shall furnish and place any necessary surfacing material to avoid loss of time due to muddy conditions;

# Lunch Facilities

CONTRACTOR shall provide any necessary lunch facilities for their forces;

# Removal of Equipment Materials from WORK SITE

All equipment, materials, supplies and tools leaving the premises are to be accompanied by a gate pass issued by OWNER;

# Review by OWNER

Review and approval by OWNER of CONTRACTOR's rigging, scaffolding and other construction plans shall not constitute, or be construed as, an assumption of CONTRACTOR's responsibility or liability for scaffolding or safety under the Contract or at law and does not relieve CONTRACTOR from full compliance with its legal and contractual obligations.

### END OF TECHNICAL ANNEX No1 - SCOPE OF WORKS