Engineering, Procurement & Construction Contract

SRU K-1, K-2 and 10K-1 waste heat utilization for steam production using mechanical vapor recompression (MVR) technology at public company ORLEN Lietuva  Mažeikių st. 75, Juodeikiai village, LT-89453 Mažeikiai district municipality, Lithuania

ANNEX 5

Time Schedule

| Rev. | 1 | 2 | 3 | 4 | 5 |
| --- | --- | --- | --- | --- | --- |
| Date | 2025.05.27 |  |  |  |  |

- TIME SCHEDULE

  - Contractor shall complete all the Works strictly in accordance with Milestones specified in 1 table below:

Table No 1. Time schedule

| Milestone # | Activities description | Implementation period after contract effective date, calendar days |
| --- | --- | --- |
| 1 | Technical Design preparation and State Construction Permit issue – 100% | XXX |
| 2 | M/C/I/E Detail Design “Issue for Construction”– 40% | XXX |
| 3 | M/C/I/E Detail Design “Issue for Construction”– 70% | XXX |
| 4 | M/C/I/E Detail Design “Issue for Construction”– 100% | XXX |
| 5 | M/C/I/E Materials delivery on SITE – 40% | XXX |
| 6 | M/C/I/E Materials delivery on SITE – 70% | XXX |
| 7 | M/C/I/E Materials delivery on SITE – 100% | XXX |
| 8 | M/C/I/E Construction works of MVR K-1 system – 30% | XXX |
| 9 | M/C/I/E Construction works of MVR K-1 system – 60% | XXX |
| 10 | M/C/I/E Construction works of MVR K-1 system – 100% | XXX |
| 11 | M/C/I/E Construction works of MVR K-2 system – 30% | XXX |
| 12 | M/C/I/E Construction works of MVR K-2 system – 60% | XXX |
| 13 | M/C/I/E Construction works of MVR K-2 system – 100% | XXX |
| 14 | M/C/I/E Construction works of MVR 10K-1 system – 30% | XXX |
| 15 | M/C/I/E Construction works of MVR 10K-1 system – 60% | XXX |
| 16 | M/C/I/E Construction works of MVR 10K-1 system – 100% | XXX |
| 17 | Mechanical Completion | XXX |
| 18 | Performance Test implementation | XXX |
| 19 | State Commissioning Acceptance | XXX |
| 20 | Documentation handover to OWNER – 100% | XXX |

  - Contractor is obligated to finish all above milestones within the indicated terms;

  - Contractor is obligated to achieve exact execution status indicated for each of above milestones;

  - In case Contractor fails to achieve all or any of determined milestones as per Table No1 within indicated terms and conditions, the Owner shall be entitled to apply rights/liquidated damages as stated in GTC Annex 9 - Payment schedule and liabilities.

REQUIREMENTS FOR PREPARATION OF TIME SCHEDULE IN TENDER PHASE

The TIME SCHEDULE shall be attached to the CONTRACT and shall present the interrelationship between the various elements of the WORKS required under this CONTRACT.

The TIME SCHEDULE shall be Level 2 according to Critical Path Methodology i.e.

Level 2 Schedule also called a Summary Master Schedule (SMS). Maintained as a summarization of the Level 3 Project Coordination Schedule(s). It depicts the overall project broken down into its major components by area and is used for higher-level management reporting.

Frequently developed by as part of its commitment planning for the project and then maintained by the CONTRACTOR. Can be used to integrate multiple contractors / multiple project schedules for the overall control of a program. It will include the Level 1 information expanded to show activities by area or major item of capital equipment. Should demonstrate the driving paths for structures and major process systems at the CSI Division Level (e.g., Earthwork, Foundations, Framing, Enclosure and Process Equipment), based on the project method statement. Audiences for this type of schedule include, but are not limited to general managers, sponsors, and program or project managers.

The TIME SCHEDULE shall include detailed activities and sequence of all activities needed for the orderly performance and completion of every separable part of the WORKS in order to meet the milestones stipulated for each major event as well as the activities listed in ANNEX 7 - PAYMENT SCHEDULE. The TIME SCHEDULE shall show mobilization and demobilization activities for CONTRACTOR’s on-Site Work. CONTRACTOR shall be responsible for utilizing all available information as required to establish the availability of materials and equipment to support scheduled activities.

DETAILED TIME SCHEDULE REQUIREMENTS

The CONTRACTOR shall submit to the OWNER for approval DETAILED TIME SCHEDULE (in editable format), 60 Days after Effective Date of the Contract.

The DETAILED TIME SCHEDULE shall be Level 3 according to Critical Path Methodology i.e.

The Level 3 schedule spans the whole of the project and is used to support the monthly report. It includes all major milestones, major elements of design, engineering, procurement, construction, testing, commissioning and/or start-up. If the Level 4 schedules are primarily developed by trade/sub-contractors, during the initial phases of the project the Level 3 schedule provides the schedule framework and constraints used by the subcontractors to develop their tenders. During the execution phase of the project this schedule defines the overall critical path and is the primary coordination tool for the overall project. Audiences for this type of schedule include, but are not limited to program or project managers, CMs or owner’s representatives, superintendents, and general foremen.

Level accuracy is presented in the table below.

Clarification:

Each level contains as minimum requirements of previous one and is additionally developed according to description.

The DETAILED TIME SCHEDULE shall, as a minimum, show the following:

(a)	the order in which the CONTRACTOR proposes to carry out and execute the WORKS (including design, purchase orders for long lead equipment, manufacture, delivery to the SITE of the EQUIPMENT and MATERIALS, construction, erection, PRE-COMMISSIONING, COMMISSIONING, START-UP, STABLE OPERATION and PERFORMANCE TESTS),

(b)	the times for submission and approval of the TECHNICAL DOCUMENTATION,

(c)	the total and activity free float for main activities, and the critical path of the WORKS,

(d)	the relationship between all the various CONTRACTOR’S activities, and the impact of each such activity on the critical path of the WORKS,

(e)	all CONTRACTOR’S activities that are linked logically in the period from the EFFECTIVE DATE to the PROVISIONAL ACCEPTANCE CERTIFICATE in a manner allowing to track the impact of delay and acceleration of each activity upon the remaining CONTRACTOR’S activities under the CONTRACT,

(f)	the scheduled date of start and completion for each CONTRACTOR’S activity.

The DETAILED TIME SCHEDULE shall constitute a basis for manpower and/or manning histograms and s-diagrams of the CONTRACTOR’S PERSONNEL in the performance of the WORKS (overall and per discipline). CONTRACTOR shall provide together with DETAILED TIME SCHEDULE: manpower and/or manning histograms and s-diagrams of the CONTRACTOR’S PERSONNEL to be updated on the monthly basis.