1. General.

M26-LK-2 package covers works to be performed in Operations Subdivision No 1 Complex LK-2 in 2026.

Performing works listed in the job list of the work package M26-LK-2 and its attachments. Blinding off the pressure vessels, preparing them for steaming and purging. Where necessary, demounting equipment indicated in diagrams (pipe sections, valves, level meters, thermowells, level columns, etc.). Cleaning vessels and their elements using high pressure equipment. Preparing vessels for inspection and NDT in accordance with Inspection Plans (IP) provided.  If any defects are identified by inspection, fixing the defects and preparing repair documentation as required by OL procedure BM-2. Additional repairs will be based on hourly rates and therefore Contractor must indicate hourly rates for different personnel (job positions) in its proposal.

2. Attachments.

2.1 M26-LK-2 job list (M26-LK-2_Job list.pdf). 2.2 Pressure vessel inspection plans, blinding and repair diagrams (M26-LK-2_Attachments.zip). 2.3. Schedule of preparation of pressure vessels for inspection with shift timing for each vessel.

3. Description and specifics of work.

3.1. General requirements.

All maintenance and repair works under package M26-LK-2 and its attachments shall be performed at the time of preparation of vessels for internal inspection.

3.2. Work description.

- All works shall be performed according to the provided Job List. Detailed scopes of work for each vessel are provided in the attachments to the Job List: tank, line blinding diagrams, inspection plans, etc. - CONTRACTOR shall install blinds and prepare pressure vessels for steaming in accordance with provided diagrams. If agreed, the same diagram can be used for blinding and steaming (depending on the process flow). CONTRACTOR shall install special steam/drain nozzles, blinds/special blinds, and spacer rods. - CONTRACTOR shall demount the elements of vessels in accordance with provided diagrams. It is required to demount equipment indicated in diagrams (pipeline sections, valves, level gauges, level columns, etc.). CONTRACTOR shall repack the flanged connections indicated in diagrams by replacing gaskets and studs. - CONTRACTOR shall wash vessels using high pressure equipment and dry them after washing. - Where necessary, CONTRACTOR shall remove contaminants from the internal surface of the vessels. - CONTRACTOR shall prepare vessels for planned inspection and revision in accordance with IP provided by the OWNER. - Depending on vessel registration, CONTRACTOR shall hand vessels over to an accredited body inspector or OL Technical Supervision Engineer for internal inspection or hydrotest (HT) control. - After completing repairs, CONTRACTOR shall reinstall blinds where necessary (installation points to be indicated by OWNER), perform hydrotest (if repairs were made) and hand vessels over to an accredited body inspector or ORLEN Lietuva Technical Supervision Engineer for evaluation. - CONTRACTOR shall perform intermediate hydraulic tests in accordance with the provided SOWs (to check the tightness). - CONTRACTOR shall remove water from pressure vessels where necessary. - CONTRACTOR shall remove blinds upon completion of all works under the inspection plan and receipt of permission from work coordinator. - CONTRACTOR shall fabricate, if necessary, in accordance with SOWs provided, all equipment necessary for repairs. - CONTRACTOR shall have the capability and resources to carry out post-inspection repairs of vessels and subject to agreement with the OWNER on the repair method statement, perform the repairs at the hourly rates specified in the contract if necessary.

3.3. Special requirements (if any).

1. Requirements to Contractor are provided in qualification and technical criteria. 2. Contractor shall exercise the coordination of materials. Contractor’s material coordinator shall collect the materials from the Owner’s warehouse no later than one day prior to the start of the works, provided that the materials are available in the warehouse. OWNER will perform transportation of materials inside the Company’s territory. Coordination of materials shall be in line with OL Rules for Coordination of Materials. 3. In its proposal, the CONTRACTOR shall take into account and commit to perform the works according to the schedule provided by the OWNER and present its own work execution schedule with the indication of labor resources, number of people for each vessel, as required under technical criteria. 4. If defects identified during inspection require repairs, Contractor shall be able to repair them and develop repair documentation as required by OWNER’S Procedure BM-2. 5. As for post-inspection repairs, the Contractor shall be responsible for immediate preparation of repair documentation as per OL Procedure BM-2. CONTRACTOR shall be responsible for organizing required NDT prior to hydrotesting/handover to inspector. Final documentation shall be submitted within ten days after the completion of works. The requirements applicable to repair documentation are defined in Procedure BM-2. 6. OWNER’S requirement – at least 1 work manager for 15 workers under direct supervision. 7. Mobilization costs shall be included in the price of works. 8. Office and tools trailers (including mobilization / demobilization) shall be included into the price of works. OWNER will provide a place for such containers and the possibility to connect utilities. 9. CONTRACTOR shall have its own certified electrical engineer authorized to perform electrical connections/disconnections of CONTRACTOR’S equipment to/from OWNER’S power networks/facilities. 10. CONTRACTOR shall appoint an entry attendant for inspections inside pressure vessels. 11. CONTRACTOR shall install temporary illumination >300Lx inside all pressure vessels indicated in this Work Package in accordance with the established procedure. Illumination is required for cleaning and inspection works. 12. CONTRACTOR shall have staff trained to use compressed air equipment. Equipment shall be furnished by CONTRACTOR. 13. OWNER reserves the right, without a separate explanation but subject to agreement with CONTRACTOR, to adjust the deadlines for handing individual pressure vessels over to inspectors, taking into account weather conditions and OWNER’S production needs. OWNER will inform CONTRACTOR about any changes not later than 10 business days prior to the date of particular works.

3.4. Requirements for work execution and documentation.

1. Method statement shall be developed for all repair works that involve welding according to OL requirements and agreed with responsible OL specialists. 2. CONTRACTOR shall develop repair documentation for all completed repair works according to OL requirements. Agreed and approved documentation shall be submitted to OL. 3. All disassembled and assembled flanged connections shall have the attached information plates (tags) indicating the name of CONTRCTOR having performed the works, gasket type, ID of metalworker (from the submitted list of trained metalworkers) having assembled the flange, and the date.

3.5. Qualification and technical requirements for Contractor. Qualification and technical requirements for Contractor. Table 1

4. Materials, equipment, and services to be provided by the Owner.

1. - All materials required for the works (valves, gaskets, blinds, nuts, lubricants, rust removers, elements required for repairs of pipelines and vessels) – by OWNER; 2. Cranes and forklifts – by OWNER; 3. - Extractor for extraction/installation of tube bundles – by another contractor hired by OWNER under a long-term contract. 4. Scaffolding and insulation – by another contractor hired by OWNER under a long-term contract; 5. Non-destructive testing – by another contractor hired by OWNER under a long-term contract;

5. Materials, equipment, and services to be provided by the CONTRACTOR.

1. All the equipment required to perform the indicated works – by CONTRACTOR; 2. High pressure cleaning equipment and vacuum trucks – by CONTRACTOR; 3. CONTRACTOR shall have all welding materials required for the work to be done by it. This includes: electrodes, gas, wool for heat treatment, tools, personal protective equipment, slings, hydraulic equipment, pressure gauges, heat treatment equipment. 4. All equipment (el. equipment, distribution cabinets, cables, switches, plugs, lamps, etc.) used by CONTRACTOR in potential gas release zones shall be explosion-proof. Vehicle(s) used by the CONTRACTOR to pump out and transport sludge shall meet ADR requirements. 5. CONTRACTOR shall have connections to fire hydrants for 4 to 6 bar water supply.

6. Requirements for work completion.

- All works must be completed in accordance with the submitted and approved schedule;

2. Maintenance documentation shall be developed for all repair works and submitted to the OWNER in accordance with BM-2 requirements. 3. All pressure vessels shall be handed over to OL specialists before closing and a permit to close must be obtained for them; 4. All consumed materials shall be written off after repairs according to each work ID; 5. The remaining unused materials shall be returned to OL Warehouse; 6. Any waste generated during the maintenance shall be sorted, packed, labeled and handled according to OL requirements (approved Waste Management Plan); 7. After completion of works, the work area and territory shall be cleaned up and handed over to OL representative.

7. Requirements for work acceptance.

During the pressurization of pressure vessel, the Contractor shall assign employees to stay on duty for the elimination of possible defects and leaks.

8. Requirements for work schedule.

1. All works shall be performed according to the work schedule provided by OWNER. Note: time for preparation of vessels for internal inspection may not always match OWNER’S schedule, therefore the preparation time of each vessel shall be agreed with OWNER’S mechanical engineer and work coordinator in advance. 2. In case of operational necessity and if requested by the OWNER, it may be required to perform works on weekends, rest days and public holidays under hourly rates for different positions and coefficients established in the contract. Table 1

|  | Qualification criteria | YES/NO (if marked YES, necessary supporting documentation must be attached; otherwise, the proposal will be withdrawn from further evaluation) |
| --- | --- | --- |
| 1 | Valid certificate issued by the National Energy Regulatory Council (NERC) of the Republic of Lithuania authorizing maintenance/operation of crude processing facilities: Repair of crude oil processing units irrespective of their parameters. |  |
| 2 | List of subcontractors (if any). Where subcontractors are indicated, it shall be required to present their valid (NERC) certificates for respective works. If engagement of subcontractors is indicated though the subcontractors are not named and/or their valid NERC certificates are not provided, the proposal will be rejected or, in case of necessity, revised additionally. |  |
| 3 | A list of company welding procedure qualification records (WPQR): processes 141 and 111, for material groups FM1 and FM5, for pipes with diameter ≥ 25 mm, wall thickness from 3 mm to 24 mm. |  |
| 4 | List of Contractor’s welders with regular employment contracts (≥ 3) and their qualification data. Qualification shall be certified as per LST EN ISO 9606-1 requirements for processes 141 and 111. |  |
| 5 | A list of company employees holding employment contracts and European Welding Engineer or European Welding Technologist (IWE, EWE or IWT, EWT) qualification certificates. |  |
| 6 | Contractor shall attach a signed Job List. This will serve as a confirmation that all works have been included in the proposal. Note: in the absence of such signed lists, the proposal will be withdrawn from further evaluation. |  |
| 7 | A completed price schedule with indicated man-hours WITHOUT PRICES. In the absence of such information, the proposal will be withdrawn from further evaluation. |  |
| 8 | Work experience – where and what works were performed during the last 5 years. Experience must be appropriate to the type of works indicated in the package. In the absence of such information, the proposal will be withdrawn from further evaluation. |  |
| 9 | CONTRACTOR shall submit information on planned labor resources for each ID. In the absence of such information, the proposal will be withdrawn from further evaluation. ± 20% deviation from OWNER’S calculations is permitted. In case of a higher deviation, the proposal may be withdrawn from further evaluation. |  |
| 10 | A work schedule developed and signed by CONTRACTOR. |  |
| 11 | List of subcontractors (if any) and their labor resources planned for the execution of the works. The scope of works assigned to subcontractors cannot exceed 30 per cent of the general Contractor's scope. If works assigned to subcontractors exceed 30 percent of the entire scope, the proposal will be withdrawn from further evaluation. |  |
| 12 | Number of work managers. OWNER’S requirement – at least 1 work manager per shift of 15 workers. For this requirement, a work organization chart shall be presented. In the absence of such information, the proposal will be withdrawn from further evaluation. |  |
| 13 | CONFIRMATION that, when necessary and agreed with CONTRACTOR, CONTRACTOR will have the capability and resources to prepare individual pressure vessels for inspection in accordance with the OWNER’S production requirements rather than the schedule indicated in the Scope of Work. Without the confirmation, the proposal will be excluded from further evaluation. |  |
|  | Technical criteria | YES/NO (if marked YES, necessary supporting documentation must be attached; otherwise, the proposal will be withdrawn from further evaluation) |
| 1 | Present proof of compliance of management system with ISO 9001:2015 (LST EN ISO 9001:2015). |  |
| 2 | Present proof of compliance of environmental protection management system with ISO 14001:2015 (LST EN ISO 14001:2015). |  |
| 3 | Present proof of compliance of occupational health and safety management system with ISO 45001:2018 (LST ISO 45001:2018) or other EU occupational health and safety standard. |  |
| 4 | CONTRACTOR must have staff certified to use compressed air apparatus. All equipment shall be provided by the Contractor. CONTRACTOR must present a list of certified employees. |  |
| 5 | List of own or rented (if rented, attach rent agreement) machinery with cleaning characteristics (water flow rate, pressure), vacuum tank, high-pressure jets, transport for mobilization of machinery and people. |  |
| 6 | Number of employees with employment contracts and rigger qualification. |  |
| 7 | Present the list and qualification documents of your employees holding employment contracts and crane operation supervisor certificates. |  |
| 8 | Present the list and qualification documents of your employees holding employment contracts and pressure vessel maintenance foreman certificates. |  |
| 9 | List of available (rented) hydraulic and/or pneumatic adjustable torque wrenches (with technical characteristics and quantities) suitable for the intended works (minimum 7500 [N-m]). |  |
| 10 | List of owned/rented hydraulic expanders (with technical characteristics and quantities) suitable for the intended works. |  |
| 11 | List of owned/rented hydraulic nut cutters (with technical characteristics and quantities) suitable for the intended works. |  |

Other information required for procurement (information provided in this Item will not be sent to contractors).

CONTRACTOR shall submit a fixed price for all mechanical works listed. Additional works will be performed and paid for under a separate agreement, based on hourly rates provided in the contract.

| Description | Value | Quantity |
| --- | --- | --- |
|  | Man-hours | 0 |
|  | Labour, EUR | 0 |
|  | Materials, EUR | 0 |
|  | Equipment, EUR | 0 |
|  | Total, EUR: | 0 |

Prepared by:

Marius Lubys

Operations Subdivision No.1 Maintenance Manager