1. General.

Design and replacement of Waste water treatment shop gas detectors STM.

2. Attachments.

Attachment 1. Scope of design work and requirements (OLP02754).

Attachment 2. Example of a payment schedule

3. Description and specifics of work.

3.1. Work description.

- Contractor shall develop a design (OLP02754) in accordance with the scope of works and requirements set out in Attachment 1 and have it agreed with the Owner’s Technical Inspection and Analysis Group.

- Contractor shall perform the installation work and programming provided for in the design OLP02754 developed by Contractor.

- Contractor shall demount the old equipment, cabinets, piping, place the scrap metal in containers for disposal in accordance with OL procedures. Contractor shall clean up the site after dismantling the old equipment: remove redundant structures, seal the remaining holes in panels/cabinets, etc.;

- Contractor shall perform commissioning/start-up and hand over the system to the fire and rescue service and for metrological verification.

3.2. Special requirements (if any).

- Contractor’s proposal shall be valid for 6 months.

- If scaffolding is required for the work, the Contractor shall indicate in the proposal the preliminary quantities of scaffolding required and the terms of their use.

- For partial payments if any to be requested by Contractor, Contractor shall specify the milestones subject to payment in the schedule presented by Contractor for the tender and submits a detailed payment schedule (example of payment schedule – in Attachment No. 2). .

3.3. Requirements for work execution and documentation.

None

3.4. Qualification requirements for Contractor.

- Contractor shall be sufficiently experienced in performing this type of work, including supply of all goods, services and execution of works.

- Contractor shall have sufficient resources and equipment for the execution of works.

- Contractor shall be entitled to carry out the activities required for the execution of procurement contract. Contractor (company) and its employees shall hold certificates required for works.

- Company registration certificate or any other document proving registration in the Republic of Lithuania is required.

- A certificate issued by the State Energy Inspectorate of the Republic of Lithuania authorizing  operation of electrical facilities up to 1000 V and operation of special electrical facilities.

- Subcontractors outsourced by Contractor are subject to the same requirements as Contractor. Subcontractors shall hold certificates indicated above for the assigned part of work  granting the right to perform works in the Republic of Lithuania as required by legal acts and normative documents.

4. Materials, equipment, and services supplied by Owner.

- Owner will provide scaffolding, containers for the disposal of scrap metal. If scaffolding will be required for the works, the Contractor must specify the preliminary quantity of supplied scaffolding in the offer.

- Owner will perform the metrological verification of the system installed. If the system fails to pass the legal metrological verification due to the fault of Contractor, next verification shall be performed at Contractor's cost.

- Owner will supply ‘Det-tronics’ materials.

- Owner performs the programming of the control systems of combined pumping station No. 1, blocked pumping station No. 2, pumping station No. 10, sludge pumping station No. 1.

- Owner performs SCADA programming work in the dispatching room of the Mažeikiai OPGV.

5. Materials, equipment, and services supplied by Contractor.

- Contractor shall take care of all equipment and transport services, also materials, except for those mentioned in Article 4, needed to perform the works.

- Contractor performs all the programming and configuration of Det-tronics controllers and the interface with control systems.

6. Requirements for work completion.

- All works listed in this SOW and OLP02754 have been completed.

- Copies of Det-tronics controller programs and converter settings, passwords are provided.

- A list of Det-tronics Modbus signals is provided.

7. Requirements for work acceptance.

- As-Built documentation checked by Owner’s Technical Inspection and Analysis Group has been submitted by Contractor; Certificate of Acceptance of Electrical Equipment as Fit for Use has been issued; drawbacks indicated in the As-Built documentation review report have been fixed by Contractor.

- Contractor shall also submit As-Built design documentation in PDF format on an electronic data carrier.  Each document specified in the list of design documentation and drawings shall be presented as a separate file and the name of the file shall correspond to the designation of the particular file, with Rev. No indicated additionally.

- The worksite and its surroundings are clean, waste has been collected and removed;

- A work handover and acceptance statement has been signed between Owner and Contractor.

8. Requirements for work schedule.

- Preliminary start date - 1st quarter of 2026.

- Contractor shall submit a detailed work schedule and have it agreed with Owner.  The schedule shall take into account the delivery time of materials supplied by Owner (preliminary June 2026).

- Completion of works – 2026.12.31.

- Contractor shall be responsible for reporting on the work, also forecasting and supervision of the works.

- Contractor shall plan and provide sufficient manpower to ensure the completion of works as required by the agreed schedule.