Engineering, Procurement & Construction Contract

Public Company ORLEN Lietuva

Flare farm reconstruction

GENERAL CONDITIONS

ANNEX No.6

PROCESS GUARANTEES AND REMEDIES FOR NON-PERFORMANCE

| Rev. | 0 | 1 | 2 |
| --- | --- | --- | --- |
| Data | 10/10/2025 |  |  |

# PROCESS GUARANTEES

1.1 Fuel gas flow to pilot burners.

| Process parameter | Guaranteed process parameter | Minimum acceptable performance |
| --- | --- | --- |
| Fuel gas flow to pilot burners | ≤ As specified by CONTRACTOR in D-2, D-4 data sheets | As specified in CONTRACTOR'S data sheets or lower |

In the event that the fuel gas flow is greater than that specified in the data sheet CONTRACTOR shall, at its own expense, undertake any and all necessary corrective engineering measures, including modification of the PLANT in order to achieve a fuel gas flow to pilot burners equal to or less than specified in the data sheet.  CONTRACTOR shall commence these corrective measures within 2 month following the notification by the OWNER.

1.2 Smokeless combustion.

| Process parameter | Guaranteed process parameter | Minimum acceptable performance |
| --- | --- | --- |
| Flare gas combustion at smokeless regime with 10 t/h of steam flow. | ≤ Flare gas flow as specified by CONTRACTOR in D-2, D-4 data sheets | As specified in CONTRACTOR'S data sheets or more |

In the event that the flare gas flow (at smokeless regime) is lower than that specified in the data sheet CONTRACTOR shall, at its own expense, undertake any and all necessary corrective engineering measures, including modification of the PLANT in order to achieve a flare gas flow at smokeless regime equal to or more than specified in the data sheet.  CONTRACTOR shall commence these corrective measures within 2 month following the notification by the OWNER.

# PERFORMANCE TEST

2.1 Prior to PERFORMANCE TEST (hereinafter – test run), the CONTRACTOR shall develop a test program setting out the detailed methods to be used during the test run.    Furthermore, acceptable tolerances for all results shall be specified. The test program must be approved by the OWNER.

2.2 The test run shall be deemed to have been successfully completed if, at the time of the test run, the Plant has achieved the guaranteed parameters specified in Paragraph 1.

2.3.	If during the test run, the PLANT fails to achieve the guaranteed parameters specified in the data sheet and it is determined that this results from errors in mechanical design, manufacture or installation of the PLANT, the CONTRACTOR shall, without any delay, investigate the reasons for such failure and suggest such modifications to the PLANT or its operation as the CONTRACTOR may deem necessary for enabling the PLANT to perform as guaranteed. CONTRACTOR shall promptly carry out any modification of the PLANT, which may be deemed necessary by the CONTRACTOR to ensure that the PLANT will perform as guaranteed. All engineering services in connection with such investigation and modification shall be supplied free of charge to the OWNER by the CONTRACTOR or the CONTRACTOR shall reimburse the OWNER for the actual costs associated with the EQUIPMENT and MATERIALS, which have been incurred by the OWNER in connection with the modification of the PLANT, provided that the reasons for failure to perform as guaranteed are determined to be solely attributable to the CONTRACTOR. No later than thirty (30) days after completion of such modifications, the OWNER shall repeat the test run of the PLANT.

2.4. If during the repeated testing of the PLANT in accordance with Paragraph 2.3, the PLANT still does not meet the guarantees due to the reasons attributed to the CONTRACTOR, the CONTRACTOR shall have the right to request to perform additional modifications of the PLANT, following which the PLANT shall be tested again.

2.5. If after the second modification of the PLANT, the PLANT fails to achieve the guaranteed indicators in accordance with Paragraph 2.3 and the OWNER is not able to operate the PLANT, the CONTRACTOR shall, at its cost and expense:

2.5.1. Dismantle and remove from the territory of ORLEN Lietuva all materials and parts of the unserviceable equipment of the PLANT;

2.5.2. Dismantle and remove from the territory of ORLEN Lietuva all foundations, steel structures and debris related to the unserviceable equipment;

2.5.3. Reinstate and clean the site of the unserviceable equipment, including paving;

2.5.4. Reimburse 100% (one hundred percent) of the price already paid by the OWNER to the CONTRACTOR for the unserviceable equipment.

# REMEDIES FOR NON-PERFORMANCE

3.1 In the event that the Flares D-2 and D-4 do not achieve the guaranteed parameters described in Paragraphs 1.1, 1.2 the LIQUIDATED DAMAGES shall be 3 % (three percent) of the FIXED CONTRACT PRICE.