- General.

Public Company ORLEN Lietuva (Further – Owner) is planning to reload DHT catalyst in OS-1 LK-2 S-300 reactor R-301 during shutdown of crude oil refinery DHT unit since 02/03/2026 till 01/04/2026. External nitrogen supply and services are required for DHT unit during this shutdown: 1) Liquid nitrogen supply. 2) Cooldown reactor R-301 using liquid nitrogen. 3) Gaseous nitrogen supply/feeding for reactor R-301 and catalyst unloading equipment during spent catalyst unloading. 4) Planning, coordination, management and escort of road trucks with liquid nitrogen / unloaded ones from point of loading to the refinery, in the refinery to the unit and moving out from the refinery ensuring Owner’s general regulations and procedures for Pass System, Occupational Health and Safety.

- Attachments.

Attachment No.1_Current DHT principal PFD scheme.

Attachment No.2_Requirements for contractors performing works at AB ORLEN Lietuva, available on the website: https://www.orlenlietuva.lt/EN/ForBusiness/DocumentsForContractors/Pages/default.aspx

Attachment No 3_Unit, Reactor and Cooldown information.

Attachment No.4_LK2_R-301 scheme and possible external nitrogen connection.

Attachment No.5_Plan for Road tankers route in ORLEN Lietuva refinery.

- Description and Specifics of Work.

  - General requirements.

    - The proposal shall include all the works that are described in the Scope of Work. Any minor works not specified in the SOW, however, necessary to ensure the functionality and completeness of works, shall be considered as included into the proposal.

    - The bidder shall arrive to the location of the works in order to assess all the works (supply of materials, equipment and installation) before issue of the proposal. Any costs related to the preparation of the proposal shall be exclusively at the Contractor's expense.

    - The Contractor shall supply all equipment, labor and services, perform fabrication, installation works, work site and project management, supervision of works, provide overhead costs as well as render any other services related hereto.

    - In the event of contradictions between different documents or in case technical information is not fully presented in the Scope of Work and Attachments, The Contractor shall be obliged to draw the attention of Owner’s Project Manager to these inaccuracies and follow his instructions.

    - The Contractor shall provide its personnel with amenity-administration, sanitary facilities and shall ensure good housekeeping as well as handling practices at such facilities and at work site.

    - The Contractor shall obtain all permits and authorizations required for bringing in/out its own equipment and work tools according to Owner’s requirements.

    - In order to obtain a permit for connection of its electrical equipment to Owner’s power networks, the Contractor shall meet all the requirements of the Owner, as per Occupational Safety and Health Procedure for Contractors BDS-40. All temporary el. power connections shall be performed by the Contractor following Procedure BE-16 for Temporary Powering of Electrical Equipment.

    - Prior to works, the Contractor shall develop a waste management plan and coordinate it with the Project Manager, the Head of the Unit where the works will be performed, and the Environmental Department. The Contractor shall clean the work site at the end of each shift, sort waste generated during the works and remove it to the location indicated by the Owner. Owner’s Rules on Waste Management shall be observed.

    - All works shall be executed following the Occupational Safety and Health Procedures of Owner’s, see Attachment No.2.

    - Requirements for technical offer content:

      - Explanatory note including offered cooldown methods;

      - Calculated quantity of liquid nitrogen (t) supply and road tankers;

      - Cooldown process technology with ensured safe operation of existing pipelines, nozzles and reactor in order not to damage steal structure;

      - Constant temperature (pipelines and on reactor walls) control system and methods, amount of thermocouples;

      - Principal scheme of Contractor’s equipment connection. Can be marked on the scheme of the Attachment No.4;

      - The list, quantity and specification of offered equipment. Note: information about whole equipment dimensions is required in order to plan its possible relocation in the unit;

      - Quantity of offered personnel (recommended not less than 2 operators and 1 site manager per shift. Services are planned 24hours/day in 2 shifts (day and night);

      - Calculated cooldown diagram C°/h (catalyst/wall – 24-36 hours);

      - The schedule for design/prefabrication /supply of spargers for liquid nitrogen;

      - The detail schedule of contractor’s services operations, in hours;

      - Planning, coordination, management and escort of road trucks with liquid nitrogen / unloaded ones from point of loading to the refinery, in the refinery to the unit and moving out from the refinery (including weighting loaded and empty road tankers on the scales) ensuring Owner’s general regulations and procedures for Pass System, Occupational Health and Safety,

      - Confirmation that safety plan, waste management plan other documents according Owner’s local rules will be prepared and provided to the Owner no later than 1 month before start of Works at site;

      - Required information/parameters for connection of Contractor’s equipment such as electricity, steam, piping connection diameters and etc.

      - The Bidder shall provide the offer separated into 2 parts:

a) Cooldown with liquid nitrogen of Reactor R-301.

b) Nitrogen supply/feeding for R-301 catalyst unloading operations.

Note: Supply and delivery of liquid nitrogen, management of road tankers are mandatory for all 2 offered parts.

  - Work description.

    - Cooldown process.

Reactor R-301 is cooled by circulating the nitrogen through the reaction system. Circulating nitrogen is cooled in air coolers upstream of circulation compressor with increased draft to the max. in the heater (not operating) and heat exchanger TK-304 by circulating the diesel fuel. Please find the enclosed basic circulation diagram (see Attachment No. 1).

The Contractor shall cool down R-301 reactor in 24-30 hours below 35°C in the all beds of reactor R-301, reactor wall temperature also should be below 35°C. The contractor should pinpoint exact time of cooling down the unit and provide cooldown diagram (C°/h) with calculation in the offer. Unit, Reactor and Cooldown information see in Attachment No.3.

For catalyst cooldown process must be installed constant temperature control system. Enough quantity of temperature sensors must be installed on pipeline and nozzles at spargers installation location and on walls of reactor R-301. Output data of temperature measurements have to be seen at Contractor’s nitrogen process control skid.

    - Nitrogen supply for catalyst unloading in nitrogen atmosphere in Reactor R-301.

Catalyst unloading in reactor R-301 is planned in nitrogen environment. The Contractor must ensure constant 24h/day gaseous nitrogen supply during R-301 catalyst unloading operation. Nitrogen will be supplied for reactor R-301, vacuum unit and tools of catalyst reloading contractor. Pressure of nitrogen is up to 7 barg and shall be possibility to control pressure and flow.

Possible nitrogen connection locations see in Attachment No.4_LK2_R-301 scheme and possible external nitrogen connection.

Nitrogen supply equipment should not block/interrupt catalyst reloading operations. Contractor before provision of the offer shall select suitable location for its equipment installation and connection.

    - Contractor has to provide not less than 3 specialists (2 operators and 1 site supervisor/manager) per shift for work performance (items 3.2.1 and 3.2.2). Services are planned 24hours/day in 2 shifts (day and night);

    - Contractor is responsible for coordination entrance/exit of road tankers with nitrogen or empty into/from Owner‘s refinery territory, escort of road tankers through security gates, scales, issue of permits entrance the unit. See Attachment No.5_Plan for Road tankers in ORLEN Lietuva refinery and Owner’s Pass System Regulation, see https://www.orlenlietuva.lt/EN/ForBusiness/DocumentsForContractors/Pages/default.aspx

    - Nitrogen quantity calculation and payoff for actual used nitrogen will be performed based on weighting protocols issued after weighting on Owner‘s scales in the refinery of full (after entrance) and empty (before leaving) road tankers.

    - IMPORTANT: It isn’t allowed direct liquid nitrogen inject without temperature control of pipeline wall at nitrogen connection location. Ensure at any point of process pipeline wall temperature >-15°C (at atmosphere pressure). Sudden cooling is dangerous, and how dangerous it is must be evaluated by the Contractor. The Contractor must ensure not to damage existing pipelines, reactor and catalyst by proper control of cooling process.

  - Requirements for documentation.

    - Before start the work at site the Contractor shall develop and submit documents Occupational Safety and Health Procedure for Contractors BDS-40 (safety plan, risk assessment, waste management plan). The list of such documentation, coordination and submission procedures are provided in Attachment No. 2.

    - Before starting the work at the site the Contractor shall provide requisition for permits for entrance and vehicle, list of planned equipment for deliver before checking at the security gates.

    - Shall be provided weighting protocols of road tankers with liquid nitrogen and empty ones.

    - Cooldown report with information of temperature sensors installed on pipelines and the reactor walls.

    - Daily progress reports of performed operations and used nitrogen.

  - Qualification Requirements for Contractor.

    - To submit the copies of documents evidencing Contractor’s qualification (certificates, licenses, etc.).

    - To submit a list of similar works performed over past 3 years. The list must include the following information: the name of company, description of works, the year in which works were performed, and contact persons.

Requirements for contractors performing maintenance, reconstruction and installation works in process facilities are available on the website:

EN - https://www.orlenlietuva.lt/EN/ForBusiness/DocumentsForContractors/Pages/default.aspx

Contractor shall provide the following for the tender:

| I | GENERAL REQUIREMENTS FOR CONTRACTORS |  |
| --- | --- | --- |
| ☐ |  | Certificate issued by the State Energy Inspectorate for operation of energy facilities (the operation works listed in the certificate shall comply with the works specified in the tender materials). |
| ☐ |  | CPCC qualification certificate or authorization document for foreigners granting the right to be a contractor for special construction works. |
| ☐ |  | List of work managers (welding coordinators, quality control specialists, potentially hazardous equipment maintenance foremen) to be involved in the specific maintenance, reconstruction and installation works, copies of their qualification certificates. |
| ☐ |  | Copies of all certificates held by the company evidencing the application of quality assurance system. |
| ☒ |  | A list of subcontractors (if any). |
| II | REQUIREMENTS FOR CONTRACTORS. MECHANICAL WORKS |  |
| ☐ |  | List of welders and copies of their qualification certificates (under EN ISO 9606-1, PED2014/68EU). |
| ☐ |  | List of available welding procedure specifications (WPS) as per EN ISO 15609, and welding procedure qualification records (WPQR) as per EN ISO 156114-1. The scope of application of the WPS and WPQR shall comply with the scopes (areas) specified in the tender materials. |
| ☐ |  | List of employees trained to install flanged connections using torque wrenches. The list contain the employees' personal labels (stamps). The employees who will be installing flanged connections for pressure equipment shall be duly trained and certified under EN 1591-4. Copies of qualification certificates shall be presented. |
| ☒ |  | List of available equipment to be used for the works with its technical specifications (welding machines, beveling equipment, milling-drilling equipment for tie in to the operating units, heat treatment and preheating equipment, temperature control instruments, torque wrenches, flanged connection expanders, lifting equipment, etc.). The equipment shall be tested and inspected as required under applicable normative acts. |
| III | REQUIREMENTS FOR CONTRACTORS. Process Control and Automation Works |  |
| ☐ |  | SEI/NERC** certificates for installation and operation of energy facilities (based on type of equipment): |
| ☐ |  | installation of electrical equipment |
| ☐ |  | installation of natural gas equipment |
| ☐ |  | operation of electrical equipment |
| ☐ |  | operation of thermal equipment and turbines |
| ☐ |  | operation of natural gas equipment |
| ☐ |  | operation of LPG equipment |
| ☐ |  | operation of crude oil and petroleum product equipment |
| ☐ |  | SEI/NERC** certificate shall include the allowed activities: |
| ☐ |  | works related to operation of power networks and units up to 1000 V |
| ☐ |  | works related to operation of electrical installations up to 1000 V |
| ☐ |  | process control and maintenance of crude oil refining units |
| ☐ |  | operation of protection, automation and control systems of thermal units |
| ☐ |  | operation of automation, accounting and control systems of liquefied petroleum gas units |
| ☐ |  | CPCC qualification certificate or authorization document for foreigners granting the right to hold the position of head of special construction operations for construction works of exceptional significance. |
| ☐ |  | CPCC qualification certificate or authorization document for foreigners granting the right to hold the position of head of technical supervision of special construction operations for construction works of exceptional significance. |
| ☐ |  | CPCC qualification certificate or authorization document for foreigners granting the right to perform supervision of project part execution of special construction operations for construction works of exceptional significance |
| ☐ |  | Work Manager's certificate for operation of crude and petroleum product facilities in explosive atmosphere. |
| IV | REQUIREMENTS FOR CONTRACTORS. ELECTROTECHNICAL WORKS |  |
| ☐ |  | SEI/NERC** certificates for installation and operation of energy facilities (based on type of equipment): |
| ☐ |  | installation of electrical equipment |
| ☐ |  | installation of natural gas equipment |
| ☐ |  | operation of electrical equipment |
| ☐ |  | operation of thermal equipment and turbines |
| ☐ |  | operation of natural gas equipment |
| ☐ |  | operation of LPG equipment |
| ☐ |  | operation of crude oil and petroleum product equipment |
| ☐ |  | SEI/NERC** certificate shall include the allowed activities: |
| ☐ |  | maintenance works of power networks with voltage up to 110 kV |
| ☐ |  | maintenance works of power switchgear and substations with voltage up to 110 kV |
| ☐ |  | operation of heat stations with voltage higher than 10 MW |
| ☐ |  | operation of power network with voltage up to 110 kV, relay protection, automation and control systems |
| ☐ |  | CPCC qualification certificate or authorization document for foreigners granting the right to hold the position of head of special construction operations for construction works of exceptional significance. |
| ☐ |  | CPCC qualification certificate or authorization document for foreigners granting the right to hold the position of head of technical supervision of special construction operations for construction works of exceptional significance. |
| ☐ |  | CPCC qualification certificate or authorization document for foreigners granting the right to perform supervision of project part execution of special construction operations for construction works of exceptional significance |
| ☐ |  | Work Manager's certificate for operation of crude and petroleum product facilities in explosive atmosphere. |
| V | REQUIREMENTS FOR CONTRACTORS. DESIGNING |  |
| ☐ |  | CPCC qualification certificate or authorization document for foreigners granting the right to hold the position of Project Manager for construction works of exceptional significance. |
| ☐ |  | CPCC qualification certificate or authorization document for foreigners granting the right to hold the position of Project Part Manager for construction works of exceptional significance. |
| ☐ |  | CPCC qualification certificate or authorization document for foreigners granting the right to hold the position of Project Execution Supervisor for construction works of exceptional significance. |
| ☐ |  | CPCC qualification certificate or authorization document for foreigners granting the right to hold the position of Project Part Execution Supervisor for construction works of exceptional significance. |
|  |  | Authorization document for foreigners granting the right to be a designer of special construction works. |
| ☐ |  | CPCC qualification certificate or authorization document for foreigners shall include parts of project that are allowed for designing: |
| ☐ |  | Buildings |
| ☐ |  | Structures |
| ☐ |  | Engineering networks |
| ☐ |  | Communications |
| ☐ |  | Electrotechnical |
| ☐ |  | Process control and automation |
| ☐ |  | Fire safety |
| ☐ |  | Fire detection and alarms |
| ☐ |  | Heating, ventilation and air conditioning |
| ☐ |  | Electronic communications (telecommunications) |
| ☐ |  | Preparation for construction, and organization of civil works |
| ☐ |  | Cost estimating procedure for construction works |
| VI | REQUIREMENTS FOR CONTRACTORS. Contractor's employees shall be trained and hold all certificates proving their qualification for performance of the intended works; it may be requested to provide copies. Below are examples (for information only) of qualification certificates that are required for the execution of specific works; Contractor should not be limited by this list. |  |
| ☐ |  | Lifting cranes operations supervisor (BDS-33) |
| ☒ |  | Rigger (BDS-33) |
| ☒ |  | Steeplejack (if the works are performed at a height exceeding 5 m above ground, flooring, cover slab or working surface, where main protection used against fall from height is safety harness, the workers have to be certified steeplejacks. Reference: State Labor Inspectorate) |
|  |  | Scaffolder (BDS-11) |
|  |  | Line insulator |
|  |  | Forklift driver |
|  |  | Specialist for optical cable routing, installation of couplings, testing |
| ☒ |  | Specialist for power equipment installation and operation |
|  |  | Specialist for soil excavation, reinforcement, other works in trenches and dykes |
|  |  | Specialist for works executed in wells or other underground structures and confined spaces |
|  |  | Person responsible for heating and hot water systems |
|  |  | Workers with respiratory protective equipment (compressed air) |
| ☒ |  | Workers for works with chemical substances |

Notes:

* ☒ - Applicable; ☐ - Not applicable;

** SEI/NERC - State Energy Inspectorate (from 2019-07-01 - National Energy Regulatory Council).

- Materials, equipment and services to be provided by the Owner.

  - Scaffolding/Insulation installation/dismantling (if required);

  - Crane, Forklifts (if required);

  - Board for electricity and lighting (ATEX).

  - Connection and disconnection of spargers to Owner pipeline flanges.

  - Safety training for Contractor’s personnel.

  - Magnetic identification badges (ID) for work-site access and vehicles.

  - Work and entry permits for Contractor’s personnel and equipment.

  - Air, steam, water and electricity (if required).

  - Available on site utilities:

- Steam: 2000 kg/hr (max. 3,300 kg/hr); 8 Bar (max.25 Bar); 180 ºC (max. 260 ºC);

- Electricity: 230/400 V, 63 A;

- Compressed air: max. 4,5 Bar, min. 1000 Nm3/hr.

- Materials, equipment and services to be provided by the Contractor.

  - Verify all scope requirements at the Owner’s site and participate in kick-off meeting in 30days after or prior signing of the Contract.

  - Project risk assessment and safety plan, waste collection plan including cooperation with the Owner and Statement of Preparedness to Start Contractual Works must be submitted by the Contractor 30 days before starting works at site.

  - Mobilization/demobilization of teams and equipment, safety instructions, safety tests for supervisors, preparing and receive entry cards, permits.

  - Provision of professional, trained, certified and experienced day and night teams of personnel. (Including one English or Lithuanian speaking supervisor per shift). The quantity of personnel must be enough to finish works on time without delay (Note: not less than 3 specialists (2 operators and 1 site supervisor/manager) per shift.)

  - Provide all necessary equipment (including connection adaptors) for cooldown by liquid nitrogen and preparation of gaseous nitrogen for catalyst reloading activities in nitrogen atmosphere.

  - Supply and delivery required quantity of liquid nitrogen in order to perform cooldown of rector and for catalyst reloading activities according to the Owner’s requirements.

  - Design, prefabricate and provide spargers for cooldown by nitrogen (leave spargers to customer after job completion - optional).

  - Design, prefabricate and provide clamps (jacket) for protection the existing nozzles from low temperature impact.

  - Cooldown process technology with ensured safe operation of existing pipelines, nozzles and reactor in order not to damage reactor and pipeline metal structure. To ensure required min temperature (not less than -15°C) at connection flanges, special designed sparger, Teflon gaskets and adapter will be used. There will be no contact between Nitrogen supply line and any part of the process lines. Additionally there will be used the jacket which will be installed around the pipe and heated by steam, to ensure that cold doesn’t transfer to Owner’s process lines and connections stay above -15°C.

  - Constant temperature (pipeline on reactor walls) control system with thermos sensors and installation of this system.

  - Cooldown of reactor and its wall to 35°C not exceeding 24-30 hours

  - Responsible person for Contractor’s electrical equipment.

  - Planning, coordination, management and escort of road trucks with liquid nitrogen / unloaded ones from point of loading to the refinery, in the refinery to the unit and moving out from the refinery (including weighting loaded and empty road tankers on the scales) ensuring Owner’s general regulations and procedures for Pass System, Occupational Health and Safety.

  - Install and connect Contractor’s equipment to cool down scheme connection points.

  - Provide Personal Protection Equipment (PPE) for Contractor’s personnel, such as protective suit, helmet with fastening belt, safety shoes, safety boots, coveralls, safety glasses.

  - Hotels, meals, allowances.

  - Minivans or cars for transportation of personnel to/from, inside ORLEN Lietuva refinery.

  - Provide fuel for Contractor’s trucks, cars, equipment and perform refilling if required ensuring Owner’s general regulations and procedures.

  - Daily progress reports. Final report after work is completed and a statement of used nitrogen.

- Requirements for work completion.

  - All the works and required schedule indicated in the Scope of Work are performed and accepted by the Owner.

  - Contractor‘s equipment is demobilized from the unit, the site is cleaned, provided final report.

- Requirements for Work Handover / Confirmation of Service Completion.

  - Daily progress reports are provided to the Owner.

  - Final report including used nitrogen quantity after work is finished (Exact days for preparation to be provided by bidder) and provided to the Owner.

  - Owner and Contractor agree on used nitrogen quantity and calculations for payment. The final reports are reviewed and accepted by Owner.

  - Handover acceptance statement is filled and provided to the Owner after items 7.1, 7.2, 7.3 are implemented.

- Requirements for Work Schedule.

  - Start of LK-2 DHT Unit shutdown - 02/03/2026.

  - Mobilization, safety trainings, moving Contractors equipment into the production territory, meeting between OL project group and Contractor – 02/03/2026 (To be in the refinery in the morning 8:00am).

  - I operation – Cooldown by liquid nitrogen.

    - Preparatory works (Rig up equipment, connection of equipment 02/03_03/03/2026 (Exact hours to be defined by the bidder).

    - Installation of the sparger 03/03/2026 (22:00 – 00:00).

    - Pressure increase up to 10bar, start up compressor 04/03/2026 (00:00 – 03:00am)

    - Cooldown reactor by liquid nitrogen – from 04/03/2026 03:00am. (Exact hours to be defined by the bidder).

    - Sparger disconnection – 06/03/2026 (1 hour).

    - Rig down cooldown equipment demobilization and relocation to other location at the site for gaseos nitrogen preparation and supply into system for catalyst unloading needs – 06/03/2026 (Exact hours to be defined by the bidder).

  - II operation  - Gaseous nitrogen preparation and supply for catalyst unloading needs

    - Introducing of N2 into R-301 and equipment of catalyst unloading contractor – 06/03/2026-14/03/2026.

  - Contractor shall provide detail work schedule with the technical offer. Performance of the work shall be planned in 2 shifts x 7 days x 11 hours.

  - Information about schedule for spargers and its protection (clamp) design, manufacture and delivery has to be provided.

  - The Contractor is fully responsible for proper estimation of time needed for mobilization, safety training and preparatory works at site in order to arrive earlier.

  - There are possible minor changes regarding start dates. The exact dates will be determined by the Owner no later than 30 calendar days before commencement of work.