Attachment No 2

| Item No. | Technical criteria: | YES/NO (if marked YES, necessary supporting documentation must be attached; otherwise, the proposal will be withdrawn from further evaluation) |
| --- | --- | --- |
| 1 | Attach signed Job List. This will confirm that all works have been included in your proposal. Note: in the absence of such signed Job List, the proposal will be withdrawn from further evaluation. |  |
| 2 | Completed price table for each work package containing only man-hours WITHOUT PRICES. In the absence of such information, the proposal will be withdrawn from further evaluation. |  |
| 3 | Planned labor resources for each ID and for each shift. In the absence of such information, the proposal will be withdrawn from further evaluation. Deviation - up to -30% from OL calculations. |  |
| 4 | Present signed work schedule for the following work mode: two 11-hour shifts 7 days per week. Note: in case of failure to submit such signed schedule, the proposal will be rejected. |  |
| 5 | List of subcontractors (if any) and their labor resources planned for the execution of the works. The scope of works assigned to subcontractors cannot exceed 30 per cent of the general Contractor's scope. If works assigned to subcontractors exceed 30 percent of the entire scope, the proposal will be withdrawn from further evaluation. |  |
| 6 | Confirmation of the capability to perform simultaneous cleaning of piping and pressure vessels at least in 3 locations at the same time. Minimum 3 high pressure cleaning machines in each shift are required. The works shall be organized in such manner that there is sufficient number of people and equipment for the performance of cleaning/flushing works. |  |
| 7 | Indicate the number of employees in each brigade. If such information is absent, proposal will be rejected. The number of crews must correspond to the work schedule. Presentation of this information together with work schedule is preferred. |  |
| 8 | Specify exactly what equipment (present technical characteristics) and what quantity of it will be assigned to each brigade. The quantity of equipment must correspond to the number of brigades because works will be performed at the same time. If the quantity of equipment is lower than the number of brigades, or if the specified equipment operates at a pressure below 1000 bar and a flow rate below 100 l/min, the proposal will be rejected. Presentation of this information together with work schedule is preferred. |  |