1. General.

Mechanical works under the OS-2 S-200 Work Package M14_FCC-R-202-KORP to be performed during the 2027 Turnaround. Mechanical contractor shall carry out the works indicated in Job List of Package M14_FCC-R-202-KORP and its attachments. Dismantling of clamp installed for R-202 reactor-regenerator under design OLP02905, repair of R-202 vessel shell and restoration of access platforms under design OLP02925, post-inspection repair of R-201 reactor of heat insulation (concrete lining) of reactor block, R-202 reactor-regenerator, KR-201 heater, D-201, B-206, T-202 vessels, preparation and submission of maintenance documentation to the Owner’s representatives. Contractor shall plan its resources so that it can perform additional post-inspection maintenance works of refractory of reactor block and internal equipment of installations, if needed. Scope of additional repair works is usually 5-20% of the main Scope of Works. These additional works shall be remunerated under a separate agreement based on the hourly rates.

2. Attachments.

2.1. The Job List of Work Package M14_FCC- R-202-KORP. 2.2. R-202, R-201, D-201, B-206, KR-201 diagrams, logbooks, diagrams of manway dismantling and repair, material specifications. 2.3. R-202 clamp installation design OLP02905.zip 2.4. R-202 vessel shell and access platform repair design OLP02925.zip 2.5. R-202 general layout design drawing. 2.6. OWNER’S anti-corrosive coating and painting specification OL-TR-CR-011 rev00. 2.7. UOP specifications for reactor block refractory installation (.zip) 2.8. OWNER’S Procedure BM-2 (.pdf) 2.9. Attachment No. 1. Hourly Rates.

3. Description and specifics of work.

3.1. General requirements.

3.1.1 CONTRACTOR shall perform all maintenance works under the Job List of the Work Package M14_FCC-R-202-KORP according to the presented repair preparation, repair and manway diagrams, repair projects OLP02905 and OLP02925. According to the preliminary Turnaround schedule, the unit shutdown is planned to commence on 3 May 2027, and the commissioning activities are scheduled to be completed by 7 June 2027. Unit shutdown shall preliminary take 2.5 days, start-up after maintenance shall preliminary take 3 day. 3.1.2. Prior to the commencement of works, the Contractor shall prepare a waste management plan and submit it to the Owner for approval. The waste management plan shall be agreed with the Owner’s Project Manager, the Head of Operations, and a specialist from the Environmental Department. All generated waste shall be handled in accordance with the approved waste management plan and in compliance with the Owner’s Waste Management Rules. 3.1.3. In accordance with ORLEN Lietuva OHS Procedure for Contractors BDS-40 (available at https://www.orlenlietuva.lt/EN/ForBusiness/DocumentsForContractors/Pages/Occupational-Safety-and-Health-Documents.aspx), the Contractor shall prepare an Occupational Health and Safety Plan. 3.1.4. The Contractor shall prepare welding procedure specifications (WPS) and agree them with engineers from the Owner’s Equipment Technical Supervision and Materials Analysis Group and experts of accredited body. 3.1.5. The Contractor shall obtain all permits and approvals required to bring its equipment into and execute works in the Owner’s territory. 3.1.6. To obtain a permit to connect its electrical equipment to the Owner’s power network, the Contractor shall comply with all Owner requirements set forth in ORLEN Lietuva Occupational Health and Safety Procedure for Contractors BDS-40. 3.1.7. The Contractor shall establish a temporary site for preparatory works and storage of materials. The Contractor shall be responsible for the safety of the temporary site and for the protection of materials stored therein during the execution of the works. The location and required area of the temporary site shall be agreed with the Owner’s Project Manager, Head of Operations, OHS Specialist, and the Fire and Rescue Service. All materials required for the establishment of the temporary site (including site preparation, construction, fencing if required, and other related works) shall be provided by the Contractor. 3.1.8 The Contractor’s scope of work shall include all works described or specified in the drawings (attachments) and specifications. Any minor works not explicitly indicated in the drawings or specifications, but which are necessary to ensure proper functionality and completeness of the works, shall be deemed to be included in the Contractor’s scope. 3.1.9. The Contractor shall provide its personnel with amenity, office, and sanitary facilities and shall ensure that such facilities and work areas are properly maintained and kept clean and orderly. 3.1.10. All office containers and tool containers, including their mobilization and demobilization, shall be included in the price of works. The Owner will provide designated areas for placement of the site containers and access to utility connection points (electricity, water supply, and sewerage). The Owner will provide portable toilets both within the site container area and at the process facilities. 3.1.11. The Contractor must engage a certified electrician responsible for the connection and disconnection of the Contractor’s electrical equipment. 3.1.12. A waybill is required for the Contractor to transport equipment, materials, and other items into the Owner’s premises. Each waybill shall bear an appropriate stamp or marking confirming delivery. Waybills shall be submitted to the Owner’s work supervisor together with the corresponding material write-off documentation. This requirement applies only to materials supplied by the Contractor. 3.1.13. The Contractor shall connect its temporary facilities (containers, amenity and sanitary premises, welding stations, etc.) which are necessary for execution of works by the Contractor to existing utility networks. Connection points shall be indicated by the Owner. 3.1.14 All metal waste generated during the repair shall be prepared for disposal by the Contractor. Transportation of metal waste from collection site will be arranged by the Owner. 3.1.15. All concrete waste generated during repair shall be prepared for disposal by the Contractor: steel inserts shall be removed and disposed of at Owner’s concrete waste disposal site located approximately 2 km from the worksite. - After work completion, the Contractor shall clean up the site, restore the territory and roads damaged during installation, assembly, transportation. Mobilization costs shall be included in the price of works.

3.2. Description of works.

- All works shall be performed according to the provided Job List. - Before submitting its proposal, the CONTRACTOR shall visit the worksite to familiarize with the actual conditions. - The CONTRACTOR shall perform the following works: 3.2.1. Contractor shall develop Work Execution Plan for replacement of structural shell elements of S-200 reactor-regenerator R-202, in accordance with the requirements of designs OLP02905 and OLP02925, and submit it to Owner for approval. Design must specify work sequence, crane positioning layout and equipment layout diagrams, slinging and crane lifting diagrams for replaced elements, fencing of hazardous areas, covering of hazardous openings and locations, and other safety measures ensuring safe execution of works. 3.2.2 In accordance with approved Work Execution Plan and requirements of design OLP02925, Contractor shall fabricate installation components and new access platform components from the materials provided by the Customer. Materials shall be provided by Owner. 3.2.3. In accordance with approved Work Execution Plan and requirements of design OLP02925, Contractor shall reinforce R-202 shell before demounting clamp. Before reinforcing shell, Contractor shall perform preparatory works, including dismantling and temporary modification of access platforms during period of installation works. 3.2.4. In accordance with approved Work Execution Plan, Contractor shall demount clamp installed under design OLP02905. After demounting clamp, Contractor shall transport it to separate area where the concrete lining shall be separated from clamp steel framework; Contractor shall transport metal to scrap metal area. Removed concrete lining shall be transported to concrete crushing site. 3.2.5. In accordance with requirements of design OLP02905, Contractor shall demount three existing manways and install three new manways. Before manway installation, Contractor shall remove existing lining of approximately 30 m² and shall restore the lining in accordance with design OLP02905 and requirements set forth in UOP specifications for lining (refractory). 3.2.6. In accordance with requirements of design OLP02925 and Work Execution Plan agreed with Owner, Contractor shall install new R-202 shell components. After installation of new components, Contractor shall weld new anchor refractory reinforcement elements and install new lining of approximately 160 m². 3.2.7. After R-202 internal inspection, Contractor shall perform repair of defective refractory areas in accordance with punch list requirement. The Contractor shall demount damaged refractory lining and defective anchor components. After preparation of defective areas, Contractor shall install new refractory lining (refractory area to be replaced at the bottom part of R-202 cone and on catalyst standpipes shall be 125m²; refractory area to be replaced in air distributor shall be 30m²). 3.2.8. After replacement of R-202 shell components, Contractor shall restore access platform in accordance with requirements of design OLP02925. Materials for access platform restoration shall be provided by Owner. 3.2.9. Repair of R-201 reactor refractory after internal inspection. Contractor shall remove damaged refractory and defective anchor components. After preparation of defective areas, Contractor shall install new refractory (refractory area to be replaced at the bottom part of R-202 cone shall be 30m²). 3.2.10. After opening of external manways and rebricking of manway openings, after completion of the internal inspection, Contractor shall demount brick refractory of R-201, R-202,KR-201,D-201,B-206,T-202. Manways that require removal of bricks before inspection and reinstallation before closing are attached. 3 new manways installed on R-202 in accordance with project OLP02935 will no longer require refractory brickwork installation before closing external covers. 3.2.11. Contractor shall perform repair of refractory of KR-201,D-201,B-206,T-202 after internal inspection. Scope of these repair works shall be provided after equipment has been opened. Therefore, when submitting its proposal, the Contractor shall assess its capabilities and ensure that it has sufficient available resources to carry out additional internal equipment and refractory lining repair works, which may amount to up to 20% of the scope of primary works. - Pressure vessel, heater catalyst assembly and cleaning works – by another specialized contractor of the Owner; - Pressure vessel acoustic emission testing in accordance with the program prepared and agreed with the Owner – by another contractor of the Owner; - Mechanical Contractor must take into consideration in its proposal of R-202 repair that at the end of reactor block repair period, approximately 7 days prior to commissioning of equipment, during acoustic emission (AE) testing (which takes about 2 to 2.5 days) no repair or installation works that generate noise, vibrations or otherwise affect the acoustic emission testing process can be performed. - Application of anti-corrosion coating to all repaired sections of , access platforms, supports and supporting structures. Paint systems and coating application procedures shall be agreed with the Owner and shall comply with the requirements of Specification OL-TR-CR-011 Rev.00 and project OLP02925.

3.3. Special requirements (if applicable).

- The requirements to the Contractor are provided in the qualification and technical criteria. - The Contractor shall perform coordination of materials. The Contractor’s material coordinator shall collect materials from the Owner’s warehouse no later than two months prior to the start of repairs provided that the materials are available in the warehouse. The Owner shall deliver the materials to the Contractor’s material storage site within the Owner’s territory or, if needed, shall also deliver the materials to a location specified by Contractor outside the territory of ORLEN Lietuva. Material coordination shall be conducted pursuant to Owner's Regulations of Coordination of Materials Transferred to Contractors. - Certain preparatory works and mobilization are required for the Turnaround. In its proposal, the Contractor shall take into account and undertake to perform the works according to the schedule provided by the Owner and develop a schedule for its own works with the indication of labor resources, number of crews as requested under technical criteria, as well as understand and take into consideration that other works related to the repaired equipment will be performed at the same time in the same process facility. As for post-inspection repairs, the Contractor shall be responsible for immediate preparation of repair documentation as per Owner’s Procedure BM-2. The Contractor shall be responsible for organizing and coordinating all required non-destructive testing (NDT) activities for work execution and final acceptance by an accredited inspection body inspector or by the Owner's Mechanical Integrity Control Group inspector. Final documentation shall be submitted within one month following the completion of works. The requirements applicable to repair documentation are defined in Procedure BM-2. - Owner’s requirement – at least 1 work manager per shift of 15 direct workers. - Mobilization costs shall be included in the price of the works. - Office and tool site containers (including mobilization / demobilization thereof) shall be included into the price of works. - The Contractor shall install temporary lighting inside vessels, heaters, reactors and hoppers for cleaning, NDT, and internal visual inspection, in accordance with the procedure established by the Owner. Illumination inside the heater or pressure vessel during the inspection shall be >300 Lx. - The Contractor shall assign an entry attendant for internal inspection and NDT. - Together with the proposal, the Contractor shall submit hourly rates by worker categories. When preparing the proposal, the Contractor shall take into account that, following inspection, additional works of up to 20 percent of the main scope may be required, and shall ensure that sufficient resources are available to perform these additional works without exceeding the established Turnaround schedule. When submitting its proposal, the Contractor shall take into account that the passenger-freight elevator in S-200 reactor block will be out of service during execution of the works. Consequently, all equipment, tools, and steel components shall be lifted using mobile cranes, and workers shall access the work areas via the access platform stairways.

3.4. Requirements for work execution and documentation.

- Work method statements (repair technology) shall be developed for all the repair works that involve welding, according to Owner’s requirements, as agreed with Owner’s specialists responsible for welding control. - Contractor shall develop repair documentation for all completed repair works according to BM-2 Procedure requirements. Once agreed and approved, the documentation shall be provided to engineers of OWNER’S Mechanical Integrity Control Group and/or to the inspector of accredited body. - All disassembled and assembled flanged connections shall be labeled with information plates indicating the name of the contractor having performed the works, gasket type, ID of metalworker (from the submitted list of metalworkers) having assembled the flange, and the work performance date.

3.5. Qualification requirements for the Contractor.

v; Qualification criteria; YES/NO (if marked YES, necessary supporting documentation must be attached; otherwise, the proposal will be withdrawn from further evaluation). 1; A valid certificate issued by the National Energy Regulatory Council (NERC) of the Republic of Lithuania authorizing maintenance/operation of crude processing facilities: Maintenance of crude processing units (irrespective of their operating parameters); maintenance of tanks and their appurtenance (irrespective of volume) designed for storage of crude oil and/or petroleum products (except LPG) and other liquid fuels. In the absence of a valid certificate, the proposal shall be considered only if the Contractor undertakes to provide such a certificate to the Owner no later than two months before the commencement of works, i.e., by 1 March 2027 at the latest.; YES/NO. 2; A list of subcontractors (if any). Where subcontractors are indicated, their valid (NERC) certificates for respective works and similar work experience in FCC units shall be presented. If subcontractors are indicated but not named and/or valid VERT certificates are not provided, the proposal will be rejected, or, where applicable, subject to further clarification. If subcontractor does not hold a NERC certificate, it must confirm that it will provide such a certificate to the Owner no later than 1 March 2027.; YES/NO. 3; Present a list of available fitting equipment with adjustable torque indicating technical characteristics and metrological verification dates (max torque - 3000 N-m), and documents proving that staff (min. 12 employees) has been properly trained to use such equipment and certified under EN 1591– 4 (each person has to be trained not more than 4 years ago). If any of the above indicated conditions is not satisfied, the proposal will be withdrawn from further evaluation.; YES/NO. 4; List of the company's welding procedure qualification records (WPQR according to LST, EN, ISO 15614-1). Based on the works in the Package, the WPQRs required for welding of the material groups according to ISO/TR 15608 (possible groups 1, 5, 7, 8), for welding methods 141 and 111, for possible diameters (D<25 mm, D>25 mm), and for possible welding element wall thicknesses (from 3 to 24 mm) shall be available.; YES/NO. 5; List of the company's welders (minimum 15) and their qualification certificates according to ISO 9606-1 for welding methods 141 and 111, for welding materials as per the Work Package (possible welding material groups: FM1, FM2, FM3, FM4, FM5, FM6) with consideration of the indicated wall thicknesses and diameters of welded elements. Before submitting its proposal, the Contractor shall take into account the requirement that piping welders must have qualification certificates for butt welding (BW) and fillet welding (FW).; YES/NO. 6; Documents confirming that the company’s employee(s) hold the qualification of European Welding Engineer or European Welding Technologist (IWE, EWE or IWT, EWT). By submitting a proposal, the CONTRACTOR undertakes to have at least one certified engineer at the OWNER’S worksite where welding is to be performed under this SoW.; YES/NO. 7; Quality certificate on fusion welding of metals in accordance with LST EN ISO 3834-2 or LST EN ISO 3834-3.; YES/NO. 8; The signed Job List. This will serve as a confirmation that all works have been included in the proposal. Note: in the absence of such signed Job List, the proposal will be withdrawn from further evaluation.; YES/NO. 9; A completed price schedule with indicated man-hours WITHOUT PRICES. In the absence of such information, the proposal will be withdrawn from further evaluation. The Owner will compare the hours submitted by the Contractors with the Owner’s own calculated estimates. If the Contractor’s hours are more than 30 percent lower than the Owner’s estimate, the Owner will deem that the Contractor has not properly understood the specified scope, and the proposal will be withdrawn from further evaluation.; YES/NO. 10; A list of works completed in oil refineries over the last 5 years. Contractor must have experience in the repair and installation of FCC unit reactors, reactor-regenerators, vessels, and process piping in the crude oil refining industry. In the absence of such information, the proposal will be withdrawn from further evaluation.; YES/NO. 11; Contractor shall submit planned labor resources for each shift. In the absence of such information, the proposal will be withdrawn from further evaluation. Up to 20% deviation from Owner’s calculations is permitted.; YES/NO. 12; A work schedule prepared and signed by the Contractor, specifying the timelines for material supply, preparatory works, and work execution, including acoustic emission testing. Deadlines under the work schedule during shutdown may not exceed those provided by the Owner.; YES/NO. 13; Confirmation that additional post-inspection works, the scope of which may be up to 20 per cent of the main package of works, will be performed. If such confirmation is absent, the proposal may be rejected and withdrawn from further evaluation.; YES/NO. 14; A list of subcontractors (if any), including their human resources planned for the execution of the mechanical installation and repair works, shall be provided. The scope of works assigned to subcontractors shall not exceed 30% of the scope of the General Contractor. In case subcontracted works exceed 30% of the entire scope, the proposal will be withdrawn from further evaluation. Subcontractors to be agreed with the Owner prior to the Contract signature.; YES/NO. 15; A list of subcontractors (if any), including their human resources planned for the execution of the refractory (lining) dismantling and installation works, shall be provided. Scope of refractory demounting and installation work must be completed in full, as provided in the Scope of Work. Subcontractors to be agreed with the Owner prior to the Contract signature.; YES/NO. 16; Please confirm that you have understood the provided scope of work and will perform separation of concrete scrap from demounted reactor block components and will transport concrete scrap to Owner concrete collection site.; YES/NO. 17; Please confirm that you have understood the provided scope of work and that you will fabricate all items and blanks required under structural and civil part of design OLP02925 using materials provided by Owner.; YES/NO. 18; Please confirm that you have understood the scope of work and that, if awarded the contract, you will submit a Work Execution Plan for the works covered by design OLP02925 for the Owner’s review and approval no later than two months prior to the commencement of works.; YES/NO. 19; Please confirm that you have understood the scope of work and that you will furnish all materials for installation of temporary structures, supports and protectors yourself.; YES/NO. 20; Specify the number of work managers. Owner’s requirement – at least 1 work manager per shift of 15 workers. For this requirement, work organization charts shall be presented for the scope under this Work Package. In the absence of such information, the proposal will be withdrawn from further evaluation.; YES/NO. Technical criteria; YES/NO (if marked YES, necessary supporting documentation must be attached; otherwise, the proposal will be withdrawn from further evaluation). 1; Proof that Contractor’s management systems complies with ISO 90001:2015 (LST EN ISO 90001:2008).; YES/NO. 2; Proof that Contractor’s environmental management system complies with ISO 14001:2015 (LST EN ISO 14001:2015).; YES/NO. 3; Proof that Contractor’s OHS management system complies with ISO 45001:2018 (LST ISO 45001:2018) or other EU occupational health and safety standards.; YES/NO. 4; List of company employees with employment contracts and rigger qualification.; YES/NO. 5; List of company employees with employment contracts and crane operation manager (supervisor) certificates.; YES/NO. 6; List of owned/rented heat treatment equipment (including technical specifications and quantities) suitable for the execution of the planned works; YES/NO. 7; List of owned/rented hydraulic expanders (with technical characteristics and quantities) suitable for the intended works.; YES/NO. 8; List of owned/rented hydraulic nut cutters (with technical characteristics and quantities) suitable for the intended works.; YES/NO. 9; Please confirm that you understand that during the acoustic emission testing, no works from this work package list shall be carried out within testing zone 7 days before the equipment is put into operation and until the acoustic emission program has been fully completed.; YES/NO.

4. Materials, equipment, and services supplied by the Owner.

- All materials required for the installation and repair works (metal sheets, pipes, blanks for nozzles, supports, fittings for pipeline repair, valves, gaskets, blinds, studs, lubricants, rust removers, etc.) - by OWNER; - All refractory repair materials in accordance with UOP specification requirements (refractory Rescocast 17 EG – 122 tonnes; 3% alloy steel (SS) reinforcing fibers – 3.66 tonnes; refractory Rescocast 9 – 11 tonnes; refractory anchoring elements – approximately 12’000 pcs.) - by Owner (quantities indicated are preliminary). - Cranes and forklifts for loading and unloading operations – by another contractor engaged by the Owner; - Scaffolding and insulation – by another contractor engaged by the Owner; - Non-destructive testing – by another contractor engaged by the Owner; - Collection of catalyst and the cleaning of catalyst residues from R-201, R-202, D-201, B-206, and T-202 - by another Contractor engaged by the Owner. - Acoustic emission testing program and testing preparation works in FCC reactor section – by another specialized contractor of the Owner; - The Owner will indicate water and electricity connection points. - Steel materials required for the fabrication of components and blanks under design OLP02925 shall, if necessary, be delivered by the Owner to a site designated by the Contractor outside the Owner’s premises and handed over to the Contractor’s Material Coordinator.

5. Materials, equipment, and services provided by the Contractor.

- All equipment required for repair works - by the Contractor; - Contractor shall provide: welding materials (excluding spec. electrodes UTP6222MoA; Bohler Fox Nibas625; Bohler Fox CN23/12; Bohler Fox SAS-4A; Bohler Fox FFB), welding gas, wool for heat treatment, tools, perforators, refractory cutting equipment and tools, refractory gunning machines, concrete mixers and personal protection equipment, slings, hydraulic equipment and manometers. Where needed, the Contractor shall supply materials for fabrication and installation of temporary steel structures and access platforms as well as fabricate and install them. - When preparing the proposal, the Contractor shall take into account the dismantling and installation of access platforms or their components, as well as their transportation, using the Contractor’s own vehicle, to/from the temporary storage area indicated by the Owner, during the preparation of reactors for inspection. - Hydro-monitor with hydrotesting equipment – by the Contractor. - Painting materials and anticorrosive coating of repaired lines in accordance with specifications OL-TR-CR-011 (system I-A, II-A) - by Contractor or by Subcontractor engaged by the Contractor who holds the appropriate qualifications.

6. Requirements for work completion.

- All works must be completed in accordance with the submitted and approved schedule.

- Maintenance documentation shall be prepared for all repair works and submitted to the OWNER’S Technical Analysis Group engineers and experts of accredited body. - Before closing any pressure vessel manholes or covers, the vessels shall be handed over for evaluation to the Owner’s Work Coordinators or to the relevant specialists of the Technical Analysis Group, and written authorization for closing shall be obtained, confirmed by signing the closing statement. - All consumed materials shall be written off after repairs according to each work ID. - Materials that have not been used must be returned to OWNER’ Central Warehouse; - Any waste generated shall be sorted, packed, labeled and handled according to Owner’s requirements and shipped out for disposal to the place indicated in the Waste Management Plan. - After the completion of the works, submission of technical documentation, return of unused materials and write-off of used materials, cleaning of work site and territory, the Contractor shall submit a work completion statement (HAS) to Owner’s representatives, after signing of which the procedure of payment for the completed works shall be initiated.

7. Requirements for work acceptance.

- After completion of the works and during unit start-up, the Contractor shall provide three (3) fitters and one (1) supervisor on standby for three (3) days to address potential deficiencies or leaks.

8. Requirements for work schedule.

All works shall be completed within the period specified by the Owner, taking into account that the shutdown works shall be in 2.5 days, and the start-up and commissioning activities shall take approximately 3 days. - Works shall be performed in two 11-hour shifts seven days a week. - The nearest turnaround is estimated from 3 May 2027 to 07 June 2027, execution of mechanical repair works from 6 May 2027 to 3 June 2027. Preliminary dates for execution of acoustic emission testing for reactor block is from 29 May 2027 to 31 May 2027.